## Slide 1
Change Liaison Meeting
May 11th, 2022

## Slide 2: Welcome!
Thank you for being here!
Expectations:
  Please give presenters your full attention.
  Please utilize the chat functionality (bottom right) to ask questions, or wait until the end of the presentation to come off of mute and ask.
  This meeting is being recorded and will be provided in the follow-up email.

## Slide 3
AGENDA
Phase 1 Update
Phase 1 Activities
Phase 2 Update
Phase 2 Activities
Training
Engagement
Key Takeaways
Notes: Welcome Slide – Tina
Phase 1 Update
  Timeline Options – Josh or Sheena
Phase 1 Activities
  Pre-testing Process Validation – Sheena
Phase 2 Update
  Timeline (Phase 1 impact on Phase 2) – Greg
Phase 2 Activities
  Upcoming Phase 2 Workbooks
Training
  Budget Training – Sara
Engagement
  “Get Ready for Luma!” Webpage – Sara
Key Takeaways – Sheena

## Slide 4
Luma Phase 1 Update

## Slide 5
Path Forward Framework
Organization Changes (State, Infor, Deloitte, ISG)
Testing (Internal & Agency Cross Functional)
Stable Environment(s) (Technically sound configured solution)
Deployment Options (Risk & Confidence)
Realistic
Risk
Mitigation
Scope
Validate
Configure
Additional Activity (Scope of Work and Timeline)
Readiness (Awareness to Training to Support)
Impacts
Training
Support
Agency Confidence (Clear Expectations)
Path Forward

## Slide 6: Methodology to create a revised Luma Deployment Plan
Develop
Detailed
Analysis
for Selected
Scenarios
Prioritize
and Select
Scenarios
Develop
Short List
Scenarios for Further Evaluation
Evaluate
High Level
Deployment Approach Combinations
Document Potential
Deployment Approaches
Complete
Complete
Complete

## Slide 7: Deployment Option Analysis Variables
Staffing | Agency Readiness | Business Impact | Technical Configuration | Executive Support | Cost Factors
Retention of current staff - Will current staff capacity and assignment be at risk? Additional Staffing - Can subject matter expertise be made available if incremental staff is required? | Testing Support - Can the Agency complete all required testing? Training - Can the Agencies complete all required training? Deployment - Will Agencies be able to support deployment activities within the option’s timeframe? | Business Continuity - Will the day-to-day operations of the State/Agencies be disrupted? Interim Solution Implementation - Can the design & development of temporary business processes be completed as required by the option? Meet Prerequisites - Can all critical functional pre-requisites be met? | Tenant Requirements - Can the number of tenants required for development and testing be provided? Core Technical Build - Can all technical development and end-user configuration be completed to support the option? Temporary Technical Build - Can the implementation of temporary technical objects be completed within the timeline? | Organizational Alignment - Do we have support - Governance board, legislative & other stakeholder parties? | Project Implementation Costs – What is the impact of the total program implementation cost Interim Support Costs – What is the impact on cost for support between initial go live and final go live
Each option was assessed to understand the impact the State’s risk profile for go-live.
Notes: Add rationale of what is driving each of these.

## Slide 8
# | Luma Implementation Options (Post July 2022) |  | Implementation Dates |  |  |  | 
 |  |  | Oct 2022 | Jan 2023 | Apr 2023 | Jul 2023 | Jan 2024
1 | Phased: Finance First |  | Finance | HR/Pay/Time |  |  | 
2 | Phased: Finance First |  |  | Finance | HR/Pay/Time |  | 
3 | Phased: Finance First |  |  | Finance |  | HR/Pay/Time | 
4 | Phased: Finance First |  |  |  |  | Finance | HR/Pay/Time
5 | Big Bang (all functions at once) |  |  | Finance + HR/Pay/Time |  |  | 
6 | Big Bang (all functions at once) |  |  |  |  | Finance + HR/Pay/Time | 
7 | Phased: HR/Pay/Time First |  |  | HR/Pay/Time |  | Finance | 
8 | Phased: Split & Recombine |  |  | HR only |  | Finance + Pay/Time | 
Luma Implementation Options

## Slide 9
Luma Phase 1 Activities

## Slide 10: Major Project Activities – Luma Phase 1
Pre-Test Activities
Project Team
SIT
Agency
SIT
User Acceptance Testing
Cutover Execution
Go-Live
Tenant Strategy
Cutover Strategy/
Planning
Mock Cutover 1
Project SIT Plan
Mock Cutover 2
Agency SIT Plan
Mock Cutover 3
UAT Plan
Training Development
Training Content Validation
End-User Training
Training Strategy
Test Strategy
The new Agency Partnership Strategy creates an opportunity for agencies to review and comment on business processes in a controlled and managed approach to accomplish and support State critical business requirements.

## Slide 11: Agency Partnership Strategy
Pre-Test Activities
Business Process Confirmation
FRICE-W Completion
Agency Functional Confirmation
All workstreams will complete the following before we conduct the Agency Functional Confirmation activity:
    Critical Go-Live business processes are defined, configured, and unit tested
    All required Configuration Workbooks are up-to-date and complete
    Critical Go-Live business processes are confirmed by Agency Stakeholder Groups

## Slide 12: Stakeholder Groups
Scope Lock
Business Process Maps
Configurations
FRICE-W
Agency Data and Set-up
Testing
Scenarios and Scripts
System Knowledge
Design/
Reqmts
Configure
Unit Test
Document
Stakeholder Group Input
Business Process Validation
Cycle
Luma project workstreams will have an agency stakeholder group that supports workstream business process design/validation.
Each comprises 5 to 9 subject matter experts who represent one or more State agencies.
Review system and business processes
Confirm business requirements are met
Identify potential gaps
Act as a sounding board and not decision-makers

## Slide 13
Luma Phase 2 Update

## Slide 14
JUN
JUL
AUG
SEP
OCT
SIT Readiness
Tenant Build
User Stories
Test Scripts
Mitigations
Pay/Time
Compare 1
Pay/Time
Compare 2
Pay/Time
Compare 3
End User Training Developed & Validated
User Acceptance Testing
Phase 2 Start July 1 2021
50+ BPR sessions
Infor Orientations
Base Configuration
Sprint 1: Build & Test
Sprint 2: Build & Test
APR
MAY
System Integration
Testing 2
Mock Cutover3
Mock Cutover2
Mock Cutover1
Sprint 3: Build & Test
WFM 7.2 – Multi Tenant Gov Cloud
System Integration
Test 1
FRICE-W Mitigations/Scoping to Go Live
(FRICE-W): Identify, Document, and Build (testing started in March)
We are here
May 31
(now 5 weeks)
Phase 2 May 2022 Updated Roadmap through October

## Slide 15
Luma Phase 2 Activities

## Slide 16
Upcoming Phase 2 Workbooks
Learning Management System Workbook for the Luma Learning and Development Module
Performance Management Workbook

## Slide 17
Training

## Slide 18
Luma Budget
Luma Budget Team is preparing the system for the Budget FY 2024 submission.
Key points:
Rollover of Luma Budget for FY ‘24 is anticipated in the next several weeks
Emails will be forth coming with further details
A showcase of Luma Budget FY ‘24 will be scheduled prior to opening with important information to be aware of
Training will be available for:
  New Luma Budget users
  Refresher training for existing users, if desired

## Slide 19
Engagement

## Slide 20
Screenshot of Get Ready for Luma

## Slide 21
Key Takeaways

## Slide 22
Thank You!
Danielle Stevens dstevens@sco.Idaho.gov
208-332-8868
Chris Lehosit clehosit@sco.Idaho.gov 208-332-8887
Tina Fuller tfuller@sco.Idaho.gov 208-332-8867
Elijah Stearns
estearns@sco.idaho.gov 208-332-8871
Sheena Coles
SColes@sco.Idaho.gov
208-334-3100
Alex Doench
adoench@sco.Idaho.gov
208-332-8841