## Aug SCO Release
August 2026 SCO Release
Parent Case | Short Description | Release Date
CS0005828 | Contract award forms updated. Certain fields have been removed or designated as required to improve contract setup accuracy and reduce processing errors. | 2026-08-18
CS0054517 | Workflow approval visibility expanded. Agency users can now view additional workflow routing information, providing greater transparency into approval processes. | 2026-08-18
CS0056323 | Invoice rejection comments are now required. Users must provide a comment when rejecting an invoice, improving communication and reducing approval delays. | 2026-08-18
CS0082288 | New Financials workspaces available. Role-based workspaces provide centralized access to Purchasing, Accounts Payable, Asset Management, and other commonly used information and tasks. | 2026-08-18
CS0012181 | New payroll adjustment and deduction codes added. Additional deduction and retirement-related codes support payroll processing and agency-specific payroll requirements. | 2026-08-18
CS0012578 | Dual employee terminations now synchronize across all profiles. When a dual employee is terminated, associated profiles will terminate together, helping ensure accurate workforce and payroll records. | 2026-08-18
CS0013025 | Shift pattern logic updated for dual employees. Work assignments will automatically apply the appropriate inactive schedule configuration, helping prevent unintended time generation and payroll processing issues. | 2026-08-18
CS0015669 | Report creation and sharing options removed from employee and manager roles. This change strengthens data security by limiting report design capabilities to authorized users. | 2026-08-18
CS0019608 | Reporting timestamps now align with Mountain Time. Report generation times will more accurately reflect local system time, reducing confusion when reviewing report activity. | 2026-08-18
CS0038089 | Payroll distribution options added to the Request Special Incentive form. Agencies can now select whether to use or ignore payroll distribution overrides when submitting a special incentive request, providing greater flexibility when charging incentives to a different account string. | 2026-08-18
CS0086405 | New NCPERS interface added. NCPERS Enrollments and Beneficiaries. A new interface will report NCPERS enrollments with beneficiaries and withdrawals to NCPERS, eliminating the 2 step enrollment for employees. | 2026-08-18
CS0045971 | Administrators now have access to a consolidated employee profile view. Compensation, talent acquisition, human resources administration, performance, payroll, and benefits are getting a new, consolidated view of the employee profile. | 2026-08-18
CS0062204 | Certain system-delivered reports restricted to administrators. This change helps protect sensitive information and limits access to reports intended only for authorized users. | 2026-08-18
CS0064953 | New job description report available. Authorized users can generate and view job description PDFs directly from a report, improving access to position information. | 2026-08-18
CS0084138 | New learning and development notifications added. Notifications for Development Plans and Certifications help employees and administrators stay informed about important learning and certification activities. | 2026-08-18

## July 2026 Report Enterprise
July 2026 Report Enterprise
Title | State | Tags | Closed Date
UPDATE REPORT: Warrant Status Report Modification | Done | 140 | 2026-07-24 11:21
DATA: XM Field Classifications | Done | 140; Data Tree; Statewide | 2026-07-31 09:57
Report: Sherpa B8 Agency Budget Request Detail Enhancements | Done | 180; Birst; Sherpa | 2026-08-04 08:51
REPORT: U of I CSS Hours | Done | 140; 514; CS0067142; RITM0015072 | 2026-08-06 13:37

## June 2026 Report Enterprise
June 2026 Report Enterprise
Title | State | Tags | Closed Date
REPORT: ACA Hours | Done | 140; HCM; INC0144312; RITM0011018; Statewide | 2026-06-05 08:50
REPORT: COA Maintenance and Structural Relations | Done | 140; 180; 270; Statewide | 2026-06-11 13:36
REPORT: Assets for ACFR 2026 | Done | 140; Statewide | 2026-07-08 15:03
UPDATE REPORT: Legislative Handbook Reports available in Statewide | Done | 140; Statewide | 2026-07-09 15:14

## May 2026 SCO Release
May 2026 SCO Release
Number | Description | Release Date
CS0003883 | Update Resource Search screen Fields. Updates refine the Resource Search screen by adding and removing select fields, helping agency staff more efficiently process personnel actions such as rehires, terminations, transfers, and promotions across all employees. | 2026-05-26
CS0012617 | Remove all PO-PCard configurations and user actions. System updates remove PO-PCard configurations and related user actions that are no longer used, simplifying system configuration and streamlining available options. | 2026-05-26
CS0013173 | Acquisition Method needed in Luma Asset module for the annual comprehensive financial report. Updates ensure acquisition method information is captured within the Asset module to support Annual Comprehensive Financial Report reporting. | 2026-05-26
CS0013231 | Asset item fund must be required to release. Updates require Asset Item Fund information before an asset can be released, supporting statewide reporting and improving consistency in asset reconciliation and financial reporting. | 2026-05-26
CS0016355 | Add new Trial Period Dropdown Option. Updates add a new “Extension Voluntary Probation (1040)” option to the Trial Period field, allowing agencies to select this option when assigning or updating an employee’s Trial Period and supporting more accurate classification of probation extensions. | 2026-05-26
CS0029305 | Evaluate removing second link in Financial Services Management workflows after software fix. Workflow updates streamline FSM approval workflows by removing the second link previously required for approvers. | 2026-05-26
CS0031707 | Trial Period Field on Rehire. Updates clear the Trial Period field upon termination and prevent carryover on rehire, improving data accuracy and eliminating manual corrections. | 2026-05-26
CS0058413 | Bereavement Time (Earnings) time code not cascading to other leave balances. Updates support the Bereavement Time (Earnings) time code cascading to related leave balances, helping maintain accurate leave tracking and payroll processing. | 2026-05-26
CS0062235 | Change Wire Bank Transaction Code to allow end users to select wire in cash. Updates allow agencies to select Wire in Cash when processing beneficiary payments, providing a more direct option for payment processing. | 2026-05-26
CS0066365 | Support extended promotion probation hour tracking for FLSA C employees. Updates ensure extended promotion probation periods for FLSA C employees continue calculating and tracking hours beyond the initial 1,040-hour threshold | 2026-05-26
CS0074983 | PCard approvers should not approve charges they submitted as a proxy. Updates ensure approvers cannot approve their own proxy submitted charges, strengthening separation of duties and supporting security controls. | 2026-05-26
INC0149028 | Configurable Features by Data Area and ISD Access Update. Provide Export to CSV access to all users and refine ISD role usage. System updates make Export to CSV available to all users, removing the need for ISD roles for basic data extraction, while separating ISD access between FSM and HCM with updated read and write role options and requiring agencies to reassess and request new roles by July 15 to retain access and align ISD use to elevated business needs. | 2026-05-26

## May 2026 Report Enterprise
May 2026 Report Enterprise
Title | State | Tags
DATA: Data Dictionary added to FM | Done | 140; Statewide
DATA: Bring VendorAddress business class into data warehouse, add Full Vendor Address to FSM Payables Payment / Payables Invoice query subject | Done | 521; 140; Data Tree; INC0163548
REPORT: Enhancements to Agency 8 Month Temp Hours | Done | 194; INC0164303
DATA: Sherpa in Cognos POC | Done | 102; 140; 180; Data
DATA: IDD78Argument Data | Done | 140; 270; Data Tree; INC0163255; Statewide

## April 2026 Report Enterprise
April 2026 Report Enterprise
Title | State | Tags | Closed Date
UPDATE REPORT: ACFR Updates to Year End and Monthly Asset Reports | Done | 140; INC0149382 | 2026-03-30 07:41
DATA: ReconRex data in Cognos | Done | 140; 150; INC0157794 | 2026-03-30 07:41
REPORT: DHR Payscale Export | Done | 194; INC0149060; SCO0035657 | 2026-03-31 08:53
DATA: Fix Incorrect FSM Payables Invoice Payment- Payment Status data | Done | 140 | 2026-04-10 08:44
DATA: Cognos Mapping for Projects Module | Done | 260; CS0048397; INC0140494; RITM0013456; Statewide | 2026-04-10 09:57
REPORT: ACFR Salary and Benefits | Done | 140; INC0154669 | 2026-04-15 13:32

## March 2026 Report Enterprise
Mar 2026 Report Enterprise
Title | State | Tags | Closed Date
REPORT: Premium Deduction Discrepancy Reports for OGI | Done | 200; INC0092871 | 2026-02-19 08:10
DATA: PHD- 957 Emergency Contact Report | Done | 957; INC0154347 | 2026-03-04 15:40
REPORT: DAFR8260 Project Transaction Analysis | Done | 183; INC0083532; INC0149059; Low; SCO0034072 | 2026-03-09 08:26
REPORT: 270 Monthly Activity Drill Through | Done | 270; RITM0010537 | 2026-03-12 12:57
UPDATE REPORT: XM In-process Report | Done | 140; Statewide | 2026-03-13 13:59
REPORT: Vets WFM Time Distribution Enhancement | Done | 444; INC0149450 | 2026-03-17 08:44
REPORT: DAFR7101 Transaction Activity | Done | 195; 200; 231; INC0083784; INC0088583; INC0115577; SCO0034085; Statewide | 2026-03-24 08:46
UPDATE REPORT: ECF SQL Review | Done | 190; INC0157325; Statewide | 2026-03-24 08:47

## Feb 2026 Report Enterprise
Feb 2026 Report Enterprise
Title | State | Tags | Closed Date
REPORT: Predefined Filters for Custodial Reporting Groups | Done | 270 | 2026-02-03 15:28
REPORT: Employee History Report | Done | 194; Smart Sheet | 2026-02-05 13:46
UPDATE REPORT: Performance Evaluation Report | Done | 194; High | 2026-02-05 13:54
REPORT: Uncashed Payroll Warrants | Done | 110; 140 | 2026-02-09 13:58
REPORT: Revenues and Expenditures to Cash | Done | 100; 101 | 2026-02-09 15:20
REPORT: Payroll Distribution Costs | Done | 101 | 2026-02-09 15:20
REPORT: Premium Deduction Discrepancy Reports for OGI | Done | 200; INC0092871 | 2026-02-19 08:09

## Feb 2026 SCO Release
Feb 2026 SCO Release
Number | Release | Short Description
CS0005903 | February | Update PT RET ELIGIBLE work type to accrue sick leave, vacation, and holidays
CS0012282 | February | Implement HB17 updates for FLSA code and overtime
CS0013129 | February | Convert ID change requests to case workflow
CS0016222 | February | Remove State HR Approval group to reflect DHR approval model
CS0031328 | February | Add manual disapprove option for Contract Manager
CS0031333 | February | Add manual disapprove option for Sourcing Manager
CS0040538 | February | Fix PHD work assignment routing (no longer routes to BOE)
CS0044214 | February | Update OCT employees to FLSA E
CS0045814 | February | Implement INFOR integration updates
CS0045880 | February | Consolidate Requisitions menu (feature toggle)
CS0046003 | February | Add Employee Direct Reporting Relationship report (up to 10 levels)
CS0048588 | February | Add view-only payroll role
CS0063820 | February | Browser Back Button Now Supported in Expense Management (XM)

## Jan 2026 Report Enterprise
Jan 2026 Report Enterprise
Title | State | Tags | Closed Date
REPORT: 3 versions of B12 report | Done | 180; Budgets; CS0019851; RITM0010540; Statewide | 2026-01-05 08:34
DATA: STO Recon Support | Done | 140; 150 | 2026-01-05 08:35
UPDATE REPORT: Legislative Handbooks FY26 | Done | 140; Legislature | 2026-01-07 15:07
DATA: Cross-train on BIRST reporting | Done | 140 | 2026-01-12 08:48
DATA: Correct IsPrimary field in Work Assignment Audit Log | Done | 140 | 2026-01-12 13:38
DATA: Add ReconID to STO Reports | Done | 140 | 2026-01-21 09:54
DATA: ReconRex Transfers/Payroll Query IFS374 | Done | data; STO | 2026-01-22 09:18
DATA: ReconRex Cash Query IFS385 | Done | data; STO | 2026-01-22 11:48
DATA: ReconRex GL Query IFS386 | Done | data; STO | 2026-01-22 11:48
DATA: ReconRex SSG Query IFS387 | Done | data; STO | 2026-01-22 11:48
DATA: ReconRex AP Query IFS384 | Done | data; STO | 2026-01-22 11:48
REPORT: WFM Audit similar to I-Time Report | Done | 102; 140; Statewide | 2026-01-30 08:49

## 2025 Delivered Initiatives
2025 Delivered Initiatives
Category | Initiative | Description | Timing
Interfaces | Data Validation | SCO partnered with agencies to review interface data validation processes, focusing on reconciliation, improvement opportunities, and aggregation needs. Interface output metrics were provided for agency review and sign-off to confirm data accuracy for systems sending data to Luma. | Dec 2024 – Feb 2025
Interfaces | Specification Validation | SCO worked with agencies to validate functional and technical interface specifications. User acceptance testing followed to ensure requirements were met, concluding with agency approval for inbound and outbound Luma interfaces. | 2025
Security | Security Access Request Form | Statewide launch of the new Security Access Request Form. | Spring 2025
Enhancement | Navigation – Enhanced Employee Experience | Launch of the Enhanced Employee Experience, introducing a more intuitive and modern Luma interface to simplify daily tasks and improve navigation. | 2025-08-01

## Dec 2025 SCO Release
Dec 2025 SCO Release
Number | Release | Short Description
INC0131240 | December | Please create a read only version of the ApplicationAdministrator_ST role.
INC0130853 | December | Benefit Enrollment BC - ChangeEmployeeEntry and CreateWhenEmployeeEntryRequired Form Updates
INC0129127 | December | An individual from an agency was able to close a Reporting Basis - they should not have access to those menus
INC0129009 | December | Board Member - PERSI eligibility
INC0128845 | December | Create new timecode "PAF (Paid Parental Foster Leave)" - New provision in DHR PPL policy effective 10/1/2024
INC0127783 | December | Please add the Status field to the search form for the MenuSecurityConsoleList
INC0123945 | December | WFS015_W_IDRequisitionApproval work units not completing when approver unreleases requisition
INC0123587 | December | FSA start date to coordinate with all other benefit start dates. First of the month following date of hire.
INC0119642 | December | Supervisor chain can't view downstream employee appraisals
INC0118777 | December | WFS007 - Workflow Visualizer Remove Admin Node
INC0117193 | December | IHR140 ISU Employee - method needs a transaction for the calling thread errors
INC0115240 | December | Create a scheduled job to trigger Aging Off Dependent Event
INC0113423 | December | Feature Toggle: HCM and FSM Report Catalog Implmentation
INC0112627 | December | ORP TIAA contributions
INC0111334 | December | Priority 2 after 12/5 Clean up and Migrations: DPB and DPN timecodes updates: FLSA codes. Error Rule. Labor Metric Security FLSA A,C,E,L,P.
INC0109414 | December | Priority 1 after 12/5 Clean up and Migrations: Create new time Code "BER (Bereavement)" - New DHR Bereavement policy effective 7/1/2024
INC0109142 | December | IHR130 IHR140 IHR150 University Employees - Update Effective Date of Terminations
INC0106792 | December | Change Request: IFS434 incorrectly pulling duplicate payment applications against same the same invoice in outbound
INC0105825 | December | Name change request form and custom IPA
INC0103479 | December | IHR130/IHR140/150 University Employee Interfaces - Config and Interface Modification
INC0102442 | December | Please remove the leave balances from the MHC paystubs
INC0098503 | December | Workflow Visualizer - WFS007 - Pilot Project
INC0091299 | December | Add DOB
INC0085080 | December | IHR097: 290 ITD Exclude Employees that have terminated on a previous payroll from the RO290_IHR097_Balances_Luma_Prod_YYYY-MM-DD.csv file that is sent to ITD.

## Dec 2025 Report Enterprise
Dec 2025 Report Enterprise
Title | State | Tags | Closed Date
REPORT: NRD Employees | Done | 194; Modify Existing | 2025-12-03 15:37
REPORT: Employees with Position Data by Budget Unit Fund | Done | 194 | 2025-12-03 15:43
STO Reconciliation - GL/Cash detail report | Done | 140; 150 | 2025-12-10 08:52
REPORT: Overtime Reporting OBBB | Done | 140; CS0048916; INC0152039 | 2025-12-10 15:12
UPDATE REPORT: Comparative Tax Report | Done | 352 | 2025-12-16 08:51
DATA: ACFR Compensated Absences & Leave Balance Workbook | Done | 140; ACFR | 2025-12-18 08:46
REPORT: JFAC CEC Report | Done | 140; 194 | 2025-12-18 15:26
REPORT: W-4 Exemption Report | Done | 140; INC0144547; Statewide | 2025-12-19 14:52
DATA: XM Preprocess Data | Done | 140; RITM0013419; Statewide | 2025-12-19 14:52

## Nov 2025 Report Enterprise
Nov 2025 Report Enterprise
Title | State | Tags | Closed Date
DATA: I-TIME Audit | Done | 140; CHG0035494; INC0133757; Statewide | 2025-11-12 15:11

## Oct 2025 Luma Release
Oct 2025 Luma Release
Product Line | Detailed Description
Financials and Supply Management | Enables creation of evaluations across configurable timeframes (Annual, Quarterly, etc.) with up to nine evaluators per period. Introduces a business class for evaluator and approver roles, optional attachment/comment requirements on performance criteria, an approval workflow, and a dedicated evaluation workspace for setup, management, and related emails. Includes automated past-due notifications.
Financials and Supply Management | Adds Project Group as a parameter to the Generate Indirect Burdens action. Previously users could process a single project or all projects; this enhancement allows processing multiple projects within a selected group. The Project Group parameter already exists in Reverse and Delete mass jobs.
HR Talent | Prevents unnecessary constraint errors by checking whether the updated Short Description differs from the existing value. The constraint now evaluates only when a duplicate supervisor Short Description exists.
Landmark Technology Platform | Fact-row processing during cube reload can run with multiple threads. Default is one thread; administrators can configure up to four via the Reload Threads field in the AnalyticCube record, with higher limits allowed through Analytics/MaxReloadFactRowThreads.

## Oct 2025 Report Enterprise
Oct 2025 Report Enterprise
Title | State | Tags | Closed Date
DATA: PO addition to ECF Summary Report | Done |  | 2025-10-01 15:22
DATA: IBIS Validation | Done | 140; INC0149206 | 2025-10-21 15:22
REPORT: Statement of Daily Cash Position by Fund | Done | 140; 150; CS0042280; RITM0012796 | 2025-10-24 09:51
DATA: WFM tables missing data for FY23 | Done |  | 2025-10-28 17:34
UPDATE REPORT: Positions and Incumbents Modification | Done | 194; INC0149712 | 2025-10-30 14:27

## Sept 2025 Report Enterprise
Sept 2025 Report Enterprise
Title | State | Tags | Closed Date
REPORT: Deduction Premium Discrepancy Report | Done | 200; INC0144151; OGI | 2025-09-03 10:32
DATA: Prior Pay Rate | Done | 140; Controller; Critical | 2025-09-15 08:57
REPORT: Zone Balancing report | Done |  | 2025-09-18 13:16
REPORT: Cash Comparison by Fund | Done | 140 | 2025-09-18 13:18

## Aug 2025 Report Enterprise
Aug 2025 Report Enterprise
Title | State | Tags | Closed Date
REPORT: Encumbrances Detail Report | Done | 230; INC0144530; Year End | 2025-08-01 14:30
DATA: Consolidate ETL config files. | Done | 140 | 2025-08-06 15:04
REPORT: GASB 101 Replacement / PERSI Leave Balances | Done | 180; INC0144668 | 2025-08-06 15:05
INFRASTRUCTURE: Cognos ver.12 Update | Done | 140 | 2025-08-20 07:12
REPORT: DAFR0259 - Statutory Operating Transfer Recon by GO Year and Month Report | Done | 140; ACFR | 2025-08-20 12:07
REPORT: DAFR0260 - Intra Agency Operating Transfer Recon by Year and Month | Done | 140; ACFR | 2025-08-20 12:08
REPORT: DAFR0262 - Intra Agency endowment Operating Transfer Recon by Year and Month | Done | 140; ACFR | 2025-08-20 12:08
DATA: Add Appropriation Unit Description field to FSM Cash Ledger Distribution | Done | 140 | 2025-08-26 09:44
REPORT: ACFR Intercompany Billing Report | Done | 140; ACFR; RITM0010608 | 2025-08-26 11:05

## Aug 2025 SCO Release
Aug 2025 SCO Release
Number | Release | Short Description
INC0139842 | August | HCM Consolidated WebApps Project - HR Administration - Generalist 1
INC0139854 | August | HCM Consolidated WebApps Project - HR Administration - Generalist 2
INC0139859 | August | HCM Consolidated WebApps Project - HR Administration - Generalist 3
INC0139890 | August | HCM Consolidated WebApps Project - OccupationalHealth - FacilityHealthManager
INC0139896 | August | HCM Consolidated WebApps Project - EmployeeSafety - FacilitySafetyManager
INC0139900 | August | HCM Consolidated WebApps Project - EmployeeSafety - Safety Admin
INC0139905 | August | HCM Consolidated WebApps Project - Benefits - Benefits Admin
INC0139906 | August | HCM Consolidated WebApps Project - Benefits - Benefits Specialist
INC0139908 | August | HCM Consolidated WebApps Project - Compensation - CompSpecialist 1
INC0139913 | August | HCM Consolidated WebApps Project - Compensation - CompSpecialist 2
INC0139919 | August | HCM Consolidated WebApps Project - Compensation - CompSpecialist 3
INC0139920 | August | HCM Consolidated WebApps Project - Compensation - Comp Admin 1 (DFM)
INC0139921 | August | HCM Consolidated WebApps Project - Compensation - Comp Admin 2 (DHR)
INC0139923 | August | HCM Consolidated WebApps Project - Payroll - Agency Payroll
INC0139926 | August | HCM Consolidated WebApps Project - Payroll - Payroll Administrator
INC0139934 | August | HCM Consolidated WebApps Project - Learning and Development - L&D Admin
INC0139937 | August | HCM Consolidated WebApps Project - Learning and Development - Instructor
INC0139962 | August | HCM Consolidated WebApps Project - HR Administration - Position Budget Manager
INC0139964 | August | HCM Consolidated WebApps Project - Performance - Generalist 1
INC0139965 | August | HCM Consolidated WebApps Project - Performance - Generalist 2
INC0139966 | August | HCM Consolidated WebApps Project - Performance - Generalist 3
INC0139973 | August | HCM Consolidated WebApps Project - Talent Acquisition - RecruiterAdmin
INC0139974 | August | HCM Consolidated WebApps Project - Talent Acquisition - Recruiter 1
INC0139975 | August | HCM Consolidated WebApps Project - Talent Acquisition - Recruiter 2
INC0139978 | August | HCM Consolidated WebApps Project - SystemAdministration - Administrator
INC0139981 | August | FSM Consolidated WebApps Project - Assets - Asset Analyst
INC0139982 | August | FSM Consolidated WebApps Project - Assets - Asset Manager
INC0139983 | August | FSM Consolidated WebApps Project - Assets - Financials Viewer
INC0139984 | August | FSM Consolidated WebApps Project - Billing- Billing Administrator
INC0139985 | August | FSM Consolidated WebApps Project - Billing- Billing Manager
INC0139991 | August | FSM Consolidated WebApps Project - Billing- Billing Manager 330
INC0139993 | August | FSM Consolidated WebApps Project - Billing - Financials Viewer
INC0139994 | August | FSM Consolidated WebApps Project - Cash - Cash Accountant
INC0139995 | August | FSM Consolidated WebApps Project - Cash - Cash Manager
INC0139996 | August | FSM Consolidated WebApps Project - Cash - Financials Viewer
INC0139999 | August | FSM Consolidated WebApps Project - Contract - Buyer
INC0140005 | August | FSM Consolidated WebApps Project - Contract - Contract Manager AGY
INC0140008 | August | FSM Consolidated WebApps Project - Contract - Contract Manager DOP - IMPORTANT - SEE WORK NOTES
INC0140009 | August | FSM Consolidated WebApps Project - Contract - Supply Management Viewer AGY
INC0140010 | August | FSM Consolidated WebApps Project - Contract - Supply Management Viewer DOP - SEE COMMENTS
INC0140012 | August | FSM Consolidated WebApps Project - Global Ledger - Budget Analyst
INC0140013 | August | FSM Consolidated WebApps Project - Global Ledger - Chief Financial Officer
INC0140018 | August | FSM Consolidated WebApps Project - Global Ledger - Contract Manager AGY
INC0140022 | August | FSM Consolidated WebApps Project - Global Ledger - Contract Manager DOP
INC0140024 | August | FSM Consolidated WebApps Project - Global Ledger - Custodial Account Manager
INC0140026 | August | FSM Consolidated WebApps Project - Global Ledger - Contract Account Processor
INC0140032 | August | FSM Consolidated WebApps Project - Global Ledger - Financial Business Analyst
INC0140033 | August | FSM Consolidated WebApps Project - Global Ledger - Payables Manager
INC0140034 | August | FSM Consolidated WebApps Project - Global Ledger - Staff Accountant
INC0140035 | August | FSM Consolidated WebApps Project - Global Ledger - Financials Viewer
INC0140036 | August | FSM Consolidated WebApps Project - Intercompany Billing - Intercompany Billing Specialist
INC0140037 | August | FSM Consolidated WebApps Project - Intercompany Billing - Financials Viewer
INC0140064 | August | FSM Consolidated WebApps Project - Inventory - Inventory Manager
INC0140066 | August | FSM Consolidated WebApps Project - Inventory - Supply Management Viewer AGY
INC0140067 | August | FSM Consolidated WebApps Project - Inventory - Supply Management Viewer DOP - SEE WORKNOTES
INC0140068 | August | FSM Consolidated WebApps Project - Match - Match Specialist
INC0140071 | August | FSM Consolidated WebApps Project - Match - Financials Viewer
INC0140074 | August | FSM Consolidated WebApps Project - Payables - Payables Manager
INC0140077 | August | FSM Consolidated WebApps Project - Payables - Payables Payment Processor
INC0140079 | August | FSM Consolidated WebApps Project - Payables - Payables Processor
INC0140080 | August | FSM Consolidated WebApps Project - Payables - Financials Viewer
INC0140081 | August | FSM Consolidated WebApps Project - Projects- Project Accountant
INC0140084 | August | FSM Consolidated WebApps Project - Projects- Project Administrator
INC0140086 | August | FSM Consolidated WebApps Project - Projects- Project Manager
INC0140087 | August | FSM Consolidated WebApps Project - Projects- Financials Viewer
INC0140088 | August | FSM Consolidated WebApps Project - Purchasing - Buyer
INC0140089 | August | FSM Consolidated WebApps Project - Purchasing - Inventory Manager
INC0140090 | August | FSM Consolidated WebApps Project - Purchasing - Receiver
INC0140092 | August | FSM Consolidated WebApps Project - Purchasing - Supply Management Viewer AGY
INC0140093 | August | FSM Consolidated WebApps Project - Purchasing - Supply Management Viewer_DOP
INC0140094 | August | FSM Consolidated WebApps Project - Receivables - Receivables Manager
INC0140097 | August | FSM Consolidated WebApps Project - Receivables - Receivables Specialist
INC0140099 | August | FSM Consolidated WebApps Project - Sourcing - Sourcing Manager AGY
INC0140100 | August | FSM Consolidated WebApps Project - Sourcing - Sourcing Manager_DOP - SEE INCIDENT COMMENTS
INC0140105 | August | FSM Consolidated WebApps Project - Sourcing - Supply Management Viewer DOP - SEE WORK NOTES
INC0140165 | August | FSM Consolidated WebApps Project - Sourcing - Supply Management Viewer AGY
INC0140174 | August | FSM Consolidated WebApps Project - Warehouse - Warehouse Clerk
INC0140175 | August | FSM Consolidated WebApps Project - Warehouse - Supply Management Viewer AGY
INC0140176 | August | FSM Consolidated WebApps Project - Warehouse - Supply Management Viewer_DOP
INC0143774 | August | FSM Consolidated WebApps Project - Receivables - Financials Viewer
INC0143851 | August | Web App Consolidation: Remove action "Request New Invoice Payment" Financial Viewer - Accounts Payables
INC0143856 | August | Web App Consolidation: Able to add documentation as Financial Viewer - AP
INC0143858 | August | Web App Consolidation: Lock down "Budget Edit Batch" Financial Viewer - Projects
INC0143859 | August | Web App Consolidation: Lock down security to disable option to delete account analysis
INC0143860 | August | Web App Consolidation: Remove action to Create, Delete, or Update Custom Groups for Financial Viewer: Projects
INC0144432 | August | FSM Consolidated WebApps Project - Purchasing- Financials Viewer
INC0147038 | August | HCM Consolidated WebApps Project - Employee WebApp - Employee
INC0147039 | August | HCM Consolidated WebApps Project - Manager WebApp - Direct Supervisor
INC0147054 | August | FSM Consolidated WebApps Project - Approver - Approver_AGY
INC0149233 | August | FSM Consolidated WebApps - FinancialsProcessor, FinancialsAdministrator, SupplyManagementProcessor Roles - July 2025 CU Drop
INC0149309 | August | Infor OS Portal Migration
CS0016564 | August | Breadcrumbs are now available at the top of your screen, providing a clear and simple way to navigate back to previous pages without relying on the browser's back button. Each breadcrumb item represents a screen from the user's navigation path, allowing you to easily track your location within the application and jump back to earlier screens with a single click. Breadcrumbs will dynamically update based on your current position in the application, helping you maintain a smoother workflow.

## Jul 2025 Report Enterprise
Jul 2025 Report Enterprise
Title | State | Tags | Closed Date
SYSTEM: Cognos Landing Page Rework | Done | 140 | 2025-07-01 10:37
SYSTEM: Cognos field descriptions Tooltip | Done |  | 2025-07-01 10:37
REPORT: Personnel Costs by Employee | Done | 102 | 2025-07-10 08:17
DATA: New GHR Fields added to Cognos | Done | 140; INC0147466 | 2025-07-11 08:47
REPORT: DAFR8002 equivalent for Amended Statuses | Done | 140; INC0093161; SCO0034210; Statewide | 2025-07-14 08:46
DATA: Database remove _custom tables. | Done | 140 | 2025-07-16 13:26
DATA: Convert Workflow.ps1 script to Python. | Done | 140 | 2025-07-18 08:51

## Jun 2025 Report Enterprise
Jun 2025 Report Enterprise
Title | State | Tags | Closed Date
DATA: Convert Powershell | Done |  | 2025-06-03 08:31
REPORT: Payables Invoice BC Interface Data Validation | Done | 140; 7 Agencies; Audit Response; Dev | 2025-06-05 15:53
REPORT: STARS Grant Month End Replacement | Done | 190; INC0146450 | 2025-06-05 15:55
REPORT: 270 Billing AR Cash Application | Done | 2/2025; 270; INC0144707 | 2025-06-09 08:33
REPORT: Warrant Status/Federal Reporting | Done | 140; 270; Statewide | 2025-06-11 15:11
REPORT: General Ledger Transaction BC Interface Data Validation | Done | 140; Audit Response; Dev | 2025-06-13 10:54
REPORT: DAFR 5001 Vendor Intercepts | Done | 140; 240; 300; 352; INC0130676 | 2025-06-23 13:16

## May 2025 SCO Release
May 2025 SCO Release
Number | Release | Short Description
INC0144096 | May | "Acting Appointment" has been added to the Assignment Type dropdown menu to support improvements to the acting appointment process. This change allows acting roles to be clearly identified on an employee’s work assignment, providing better visibility into temporary role changes. It also supports more accurate reporting, approvals, and organizational records, improving communication and accountability
INC0131027 | May | DHR identified that two new probationary period types were created in GHR but were not mapped in WFM, resulting in hours not being tracked when these types were used. A fix is being implemented to add these values to the WFM table, ensuring proper tracking and alignment between the two systems. This update resolves data inconsistencies and reduces the risk of issues in future audits.
INC0125303 | May | A fix is being implemented to auto-populate hire forms in GHR and TA for rehires with the legacy employment number, sick leave, and CSS hours from the termed employee list. This update will save HR staff time by eliminating the need to manually search for this information during the rehire process. It also helps ensure greater consistency and accuracy in employee records
INC0118146 | May | The SCO technical team has developed an update to address an issue in the IWM002 interface, which was not consistently exporting CSS and Sick leave hours during reinstatement actions. This inconsistency led to inaccurate employee profiles in WFM, incorrect leave accrual rates, and, in some cases, employees not receiving their entitled sick leave on time.
INC0097304 | May | An issue was identified where sick leave accruals in WFM, Non-Calc Group, were being calculated using minutes worked instead of hours worked, resulting in inaccurate accruals. A fix is being implemented to ensure sick leave is calculated using hours worked, which aligns with the defined accrual rate and eliminates rounding errors.
INC0108732 | May | CPT time was incorrectly converting to JAC despite an adequate balance, has been resolved. The system previously converted CPT to JAC unexpectedly, but this behavior has now been corrected. The underlying cause of the conversion issue has been identified and addressed, ensuring that employees can use the CPT code without it being automatically converted to JAC in the future.
INC0118138 | May | Creating an interface to run with all employee personnel data to be sent to Experian for Employment Verification
INC0134134 | May | The BenefitsAdmin_ID role has been updated to grant access to the Maintenance > Processes > Secure Act Eligibility link. The Benefits Admin, Benefits Specialist, Payroll Administrator, Administrator, and Generalist_ID roles have also been updated to allow visibility of the new Secure Act section on the Employee Profile > Benefits tab, which includes the Eligible, Over Wage Limit, and Catch Up Eligible boxes.
INC0113089 | May | We enhanced the Work Assignment Search feature to support statewide employee transfers. Generalists can now initiate transfers from one agency to another without requiring actor org access at the sending agency. This change simplifies the transfer process, reduces the need for manual coordination between agencies, and helps maintain data integrity by limiting updates to the Work Unit action.
INC0139796 | May | The Pay Step field has been removed from both the Request Position Update and Request a New Position forms. This field is only relevant for positions using the NGA Military Step and Grade Schedule and should not be tied to positions directly, as it incorrectly assigns a pay rate at the position level. Going forward, Pay Steps will only appear in the Update Work Assignment action when the Step and Grade Schedule is set to NGA MILITARY.
INC0144839 | May | Two new payroll reports are now available as part of this controlled release and are accessible to all adopters: Wage Analysis – Provides detailed insights into employee wage data across pay periods. Deductions Not Taken – Identifies missed or incomplete deductions, helping ensure accurate payroll processing.
INC0141745 | May | The After Tax (Roth) option has now been added to the Voluntary Retirement Plan life events, beyond just the 457 Amount field. This change addresses employee confusion caused by discrepancies between the displayed amount and their intended Per Pay Period contribution. With this update, the system now more accurately reflects employee elections and aligns with the expanded Roth options rolling out this year.
INC0120365 | May | The rehire action in GHR and TA has been updated to only allow users to select Update Work Assignment rather than Add Work Assignment. This adjustment streamlines the process and prevents unnecessary errors by restricting the available options to the most appropriate action for rehire cases.
INC0132299 | May | Previously, when reclassifying a position or updating a position’s job, the salary structure and pay grade fields did not automatically update, resulting in manual support tickets to the DHR team. This process has now been improved—these fields are editable within the Request Position Update form, allowing agencies to make the necessary updates directly and reduce reliance on manual intervention.
INC0118488 | May | The SCO Sustainment team identified that manager structure updates were not syncing consistently across position and work assignment changes. Specifically, changes made during an Update Work Assignment did not reflect on the Position or flow through to the Manager Structure. A fix has been implemented to improve synchronization so that when a manager is updated through either a Request Position Update or an Update Work Assignment, those changes are now reflected in the Manager Structure, ensuring greater accuracy and reducing manual follow-up
INC0063906 | May | Users reported that the Position Monitoring list, including the Budget Variance Report, was taking significantly longer to load than other areas in the system. Updates have been initiated to optimize performance and reduce load times for these reports, improving the user experience for budget managers and other staff who rely on timely access to position data.
INC0140019 | May | A new BOE GHR workflow approver task has been created, and key workflows have been updated so that FLSA S transactions now route to the Board of Examiners (BOE) instead of the State Controller’s Office (SCO). The affected workflows include: Rehire (GHR and TA), Transfer (GHR and TA), Promote (GHR and TA), Add Work Assignment (GHR and TA), and Update Work Assignment. This change ensures appropriate oversight and streamlines the approval path for classified FLSA S personnel actions.
INC0119480 | May | To support transparency and streamline HR workflows, a personalization has been added to display the last approver on key actions. This enhancement applies to two specific sections and is available to all users.
INC0135802 | May | An issue was resolved where Update Work Assignment actions for Public Health Districts (PHDs) were incorrectly routed to the State Controller’s Office (SCO) for final approval when the FLSA code changed to “S.” Per the Elected Workflow rules, these should only route to SCO when the FLSA update applies to non-PHD agencies. The workflow has been corrected to ensure proper routing, preventing unnecessary delays and aligning with established approval protocols.
INC0112257 | May | An issue preventing employee enrollment in activities due to two legacy records from 2015 has been resolved. These records could not be deleted, waived, or manually updated, which blocked new enrollments. A security role fix has been implemented restoring the ability to enroll the employee successfully
INC0138274 | May | An update has been implemented to correct an issue where Comp Time payouts (CPP) were incorrectly splitting hours between account 500100 (4105) and 509000 (4175). The root cause was identified in the way hours were pulled from both Prior 6-month and Covered Comp buckets for FLSA types C, F, L, and Z. The system did not consistently apply the correct account code (509000) to both buckets.
INC0145348 | May | Significant updates have been made to the New Position and Request Position Update forms to improve transparency and support better collaboration between HR, DHR, and DFM. These changes allow for better visibility of budgeted and projected employee costs, while ensuring data integrity through role-based access.

## May 2025 Report Enterprise
May 2025 Report Enterprise
Title | State | Tags | Closed Date
REPORT: Incumbent and Positions (Kitchen Sink) | Done | 194; Smart Sheet | 2025-05-01 15:39
REPORT: Receivable Payment BC Interface Data Validation | Done | 140; 7 Agencies; Audit Response; Dev | 2025-05-02 11:05
REPORT: Receivables Invoice BC Interface Data Validation | Done | 140; 7 Agencies; Audit Response; Dev | 2025-05-02 11:05
REPORT: Census Report | Done | 180; INC0146993 | 2025-05-05 12:10
REPORT: Terminated Employees with Leave Balances | Done | 140; AU444949; INC0097027; SCO0034059 | 2025-05-05 17:02
REPORT: Retirement Sick Leave Reduction | Done | 140; B-444955; INC0097027; SCO0034059 | 2025-05-05 17:02
REPORT: Payroll Register Modifications | Done | 140; Controller; Statewide | 2025-05-09 11:32
DATA: Remediate stored procedures to ensure merging into the warehouse table | Done | 140; Dev | 2025-05-12 09:43
REPORT: Procurement Card Statement BC Interface Data Validation | Done | 140; 7 Agencies; Audit Response; Dev | 2025-05-12 09:56
REPORT: Purchase Order BC Interface Data Validation | Done | 140; Audit Response; Dev | 2025-05-12 09:56
DATA: Update ETL code to enable running more than once instance at the same time | Done | 140; Dev; ETL | 2025-05-19 09:59
DATA: Report business class/database table vs API counts comparison | Done | 140 | 2025-05-20 09:47
REPORT: Cash Ledger Transaction BC Interface Data Validation | Done | 140; 7 Agencies; Audit Response; Dev | 2025-05-23 11:03
REPORT: Cash Ledger Receipt BC Interface Data Validation | Done | 140; Audit Response; Dev | 2025-05-23 11:03
REPORT: Legal Basis Report | Done | 140; ACFR; Critical | 2025-05-28 13:05

## Apr 2025 Luma Release
Apr 2025 Luma Release
Type | Detailed Description
WFM | Response times in the WFM module will be improved.
Payroll | When an employee has an "Hours Only" earnings code such as MAD, payroll will split the Employer-Paid deduction by referencing the payroll distribution override.
Human Resources | Fix the login issues employees have when they have originally worked at a university without Luma access.
Learning and Development | Fix attaching L&D evaluations to sessions so they attach to the correct session.
Human Resources | The position update action will be fixed so agencies will not receive the "short description is already in use by another manager code" error and they should not have to enter multiple position update actions any longer.

## Apr 2025 Report Enterprise
Apr 2025 Report Enterprise
Title | State | Tags | Closed Date
REPORT: DAFR0227 GAAP Indicator Report | Done | 140 | 2025-04-02 08:44
REPORT: Asset Item BC Interface Data Validation | Done | 140; Audit Response; Dev | 2025-04-07 09:31
REPORT: Billing Invoice BC Interface Data Validation | Done | 140; 7 Agencies; Audit Response; Dev | 2025-04-08 13:23
REPORT: Cash Ledger Payment BC Interface Data Validation | Done | 140; 7 Agencies; Audit Response; Dev | 2025-04-11 08:34
REPORT: Income Statement (Statement of Activities) | Done | 140; Statewide | 2025-04-17 13:08
REPORT: IDVendor BC Interface Data Validation | Done | 140; Audit Response; Dev | 2025-04-18 11:05
REPORT: Intercompany Billing Document Line BC Interface Data Validation | Done | 140; 7 Agencies; Audit Response; Dev | 2025-04-22 15:15
REPORT: Missing Hours or Hours above / below 40 / 80 | Done | 140; 230; Statewide | 2025-04-25 08:48
DATA: Add DerivedAPItemDesc from GLTransactionDetail business class to the FSM General Ledger Transaction reporting group | Done | 270; INC0141882; Statewide | 2025-04-25 11:02
DATA: Expand Employee and Employee Address | Done | 140; Statewide | 2025-04-25 11:02
REPORT: Tax Commission Comparative Statement | Done | 352; INC0089199; SCO0034100 | 2025-04-30 13:24
REPORT: Tax Commission Comparative Statement - Distributed to and Accrued to General Fund | Done | 352; INC0089253; SCO0034101 | 2025-04-30 13:24

## Mar 2025 Report Enterprise
Mar 2025 Report Enterprise
Title | State | Tags | Closed Date
DATA: Add DepositDate field to the Receivable GL Distribution Business Class | Done | 270; INC0138336 | 2025-03-11 11:34
DATA: Project Budget to Actual update to GL | Done | 501 | 2025-03-14 08:33
REPORT: CMS Staffing | Done | 444; SCO0034109 | 2025-03-24 10:30
REPORT: Tax Commission Comparative Statement - Receipts by Tax Type from GLTransaction Data | Done | 352; INC0090168; SCO0034104 | 2025-03-25 10:34
REPORT: Tax Commission Comparative Statement - Distributions By Fund | Done | 352; INC0089543; SCO0034102 | 2025-03-25 10:36
DATA: GL Table Split | Done | 140; Infrastructure | 2025-03-27 14:17
REPORT: IPOPS Audit Report | Done | 140; INC0133757 | 2025-03-31 16:09

## Feb 2025 SCO Release
Feb 2025 SCO Release
Number | Release | Short Description
​INC0134110 | Feb | ​Employees can now submit future-dated requests to add, change, or end a voluntary retirement plan. Previously, changes had to be made using the current date, which caused issues, especially for employees planning final paycheck deductions. Now, they can select a date up to 30 days in the future, for changes to take effect on a future payroll. When choosing a future date, it should align with the pay period end date to ensure the previous pay period is posted before the change applies to the next payroll.
INC0115949 | Feb | ​Employees can now view future-dated life events under ‘My Life Events’ once they have been finalized. Previously, certain future-dated life events were not visible to employees after submission, causing confusion and uncertainty. With this update, employees will have full visibility into both their upcoming and historical life events, ensuring they can track and confirm their benefits changes at any time.
​INC0136829​ | Feb | Implement contract notification emails for expiring and expired contracts. These emails will notify state employees when a contract is nearing expiration and will be sent to the primary and secondary contacts listed on the contract (excluding supplier contacts and Ad Hoc contacts). Initially, this functionality will apply only to agency-managed contracts classified as DPA, PW, GS, or CON and can be scheduled no more than once per month. Agencies interested in using this feature should submit a support case in the Service Portal.​
INC0137345 | Feb | To ensure compliance with Idaho Code 74 and maintain proper approval processes, only SCO Administrators will have the authority to select the Confidential field on employee profiles in GHR. Previously, Generalists had the ability to select this field, but only specific employees qualify for exclusion from Transparent Idaho (TI), and approval must go through SCO. Moving forward, the Confidential field can only be selected if proper documentation is submitted via the Service Portal and approved by the SCO Admin team.
INC0135317 | Feb | To improve accuracy and alignment with legacy reporting, updates are being made to action reasons in Luma. Some action reasons will be added, inactivated, or updated to ensure consistency in personnel actions. This change will impact all Generalists when selecting action reasons for employee updates.
INC0133005 | Feb | The HR Generalist 3 role now has restricted access to employee data based on their agency’s scope, improving security and compliance. This change ensures HR Generalists can only view information relevant to their specific agency, reducing the risk of unauthorized access. It also helps maintain privacy standards and aligns with state regulations.​
INC0132421 | Feb | To prevent duplicate vacation payoffs and ensure accurate termination processing, Luma will now restrict agencies from entering multiple termination actions for the same employee. Previously, if a second termination was entered with a different effective date, it caused data issues in Luma and overpayments of leave to employees.
INC0127258 | Feb | With this update, future-dated work assignment actions, such as hires and transfers, will now automatically reflect any job or position changes made after submission but before the effective date. Previously, if an agency submitted a future-dated work assignment action and the job or position was updated, the submitted action would not reflect the change. This update ensures that future-dated actions remain accurate and aligned with the latest job and position details.
INC0087275 | Feb | The agency number will be displayed within the work item view. This allows approvers managing multiple agencies to quickly sort and filter actions by agency.
INC0087271 | Feb | Approvers will now see the effective date on all work items, making it easier to determine whether an action applies to the current, future, or prior pay period. This helps ensure payroll actions are processed on time and reduces the risk of missed approvals.
INC0077428 | Feb | A new workflow is now in place for inactivating a work assignment to prevent errors and ensure employees receive their final paycheck before the work assignment is inactivated. The workflow requires initiation and approval by agency HR for both elected and non-elected agencies, following the same logic as the Terminate process, but without requiring approval from State HR.
INC0140419 | Feb | The Options Menu, accessed by clicking the three-dot ellipsis in the upper right corner of most lists, is being restructured and renamed to improve clarity and usability. With this update, the Options Menu will now have four primary categories: Export To, Reports, Personalize, and Audit. Additionally, several menu options have been renamed for better alignment with their functions.
INC0140422 | Feb | Agency Payroll Administrators will now enter selection criteria before generating payroll reports, ensuring that only relevant and accurate data is displayed. This update improves report accuracy by reducing the risk of misinterpreting default data or generating irrelevant results. The system also improves efficiency by filtering data upfront, speeding up report generation.
INC0127552 | Feb | This fix addresses an issue where the NONPAYOUT classification was missing, causing Other Pay Rates to be incorrectly included in leave payoffs, which should only use the base rate of pay. By automatically assigning NONPAYOUT to Other Pay Rate actions, this update ensures that leave payoffs are processed accurately.
INC0125752 | Feb | Payroll Administrators can now access and view the time records they’ve submitted, addressing previous issues where initiators couldn’t track their own submissions. This change eliminates the need for additional requests and ensures administrators can confirm the accuracy of their time records. The result is improved efficiency and accountability in payroll processing.
INC0127377 | Feb | Users can delete a surplus disposal before final submission to the public website, allowing them to: Delete the surplus disposal entry, Remove the surplus date from the asset, Uncheck the surplus checkbox on the asset
INC0073765 | Feb | If employees update their timesheet after manager approval, it will become unauthorized and require manager re-approval. This ensures any changes, like timecodes or hours, are reviewed before payroll processing, preventing errors in payments. The update begins with timesheets for the period 2/16-3/1, paid on 3/14, and only affects those modified before the lockout period.

## Feb 2025 Report Enterprise
Feb 2025 Report Enterprise
Title | State | Tags | Closed Date
DATA: Please add Merchant data item in FSM GlobalLedgerTransactions Reporting Group | Done | 270; INC0122642 | 2025-02-05 15:09
DATA: HoldCode field in Payables Payments | Done | 140 | 2025-02-13 07:08
DATA: Non-Confidential Earnings Codes | Done | 140; Dev | 2025-02-14 13:03
REPORT: TATRS to Luma Cash Reconciliation | Done | 140; 150; INC0139061 | 2025-02-19 13:20
REPORT: DAFR8310 Revenue Status by Fund / Program | Done | 180; 200 | 2025-02-19 14:58
DATA: Add Description Fields for all Finance Dimensions in Cognos Reporting Groups | Done | 140 | 2025-02-27 08:22

## Jan 2025 Report Enterprise
Jan 2025 Report Enterprise
Title | State | Tags | Closed Date
REPORT: DAFR8180 Trial Balance by Fund/GL Account/ Transaction Code | Done | 102; 245; 300; INC0101834; INC0131685; INC0137024; SCO0034098 | 2025-01-07 09:15
Report: Exhibit A - Employee Counts By Agency | Done | 140; Controller | 2025-01-08 08:40
Report: Exhibit B - 10 Year State Employee Count | Done | 140; Controller | 2025-01-08 08:40
REPORT: Agency Heads | Done | 194; Luma Report; Medium | 2025-01-08 09:32
REPORT: Vacancy Report | Done | 194 | 2025-01-21 11:02
REPORT: Expense Management Report | Done | requirements gathered by BA | 2025-01-21 13:24
REPORT: WFM Timesheet Extract Report | Done | HCM; INC0078244; SCO0034050 | 2025-01-23 10:22
ETL: EIS Implementation | Done |  | 2025-01-30 15:12
DATA: Add Project Code to HCM Employee Payments | Done | 177; INC0109774 | 2025-01-31 07:49

## Nov 2024 SCO Release
Nov 2024 SCO Release
Number | Release | Short Description
INC0131240 | November | Please create a read only version of the ApplicationAdministrator_ST role.
INC0130853 | November | Benefit Enrollment BC - ChangeEmployeeEntry and CreateWhenEmployeeEntryRequired Form Updates
INC0129127 | November | An individual from an agency was able to close a Reporting Basis - they should not have access to those menus
INC0129009 | November | Board Member - PERSI eligibility
INC0128845 | November | Create new timecode "PAF (Paid Parental Foster Leave)" - New provision in DHR PPL policy effective 10/1/2024
INC0127783 | November | Please add the Status field to the search form for the MenuSecurityConsoleList
INC0123945 | November | WFS015_W_IDRequisitionApproval work units not completing when approver unreleases requisition
INC0123587 | November | FSA start date to coordinate with all other benefit start dates. First of the month following date of hire.
INC0119642 | November | Supervisor chain can't view downstream employee appraisals
INC0118777 | November | WFS007 - Workflow Visualizer Remove Admin Node
INC0117193 | November | IHR140 ISU Employee - method needs a transaction for the calling thread errors
INC0115240 | November | Create a scheduled job to trigger Aging Off Dependent Event
INC0113423 | November | Feature Toggle: HCM and FSM Report Catalog Implmentation
INC0112627 | November | ORP TIAA contributions
INC0111334 | November | Priority 2 after 12/5 Clean up and Migrations: DPB and DPN timecodes updates: FLSA codes. Error Rule. Labor Metric Security FLSA A,C,E,L,P.
INC0109414 | November | Priority 1 after 12/5 Clean up and Migrations: Create new time Code "BER (Bereavement)" - New DHR Bereavement policy effective 7/1/2024
INC0109142 | November | IHR130 IHR140 IHR150 University Employees - Update Effective Date of Terminations
INC0106792 | November | Change Request: IFS434 incorrectly pulling duplicate payment applications against same the same invoice in outbound
INC0105825 | November | Name change request form and custom IPA
INC0103479 | November | IHR130/IHR140/150 University Employee Interfaces - Config and Interface Modification
INC0102442 | November | Please remove the leave balances from the MHC paystubs
INC0098503 | November | Workflow Visualizer - WFS007 - Pilot Project
INC0091299 | November | Add DOB
INC0085080 | November | IHR097: 290 ITD Exclude Employees that have terminated on a previous payroll from the RO290_IHR097_Balances_Luma_Prod_YYYY-MM-DD.csv file that is sent to ITD.

## Oct 2024 Luma Release
Oct 2024 Luma Release
Type | Detailed Description
Enhancement | After Interfacing the AssetImport records, AssetManagementInterfaceResult record is created. This update will add a delete action to the list allowing users to delete these records which will purge the records from the business class.
Enhancement | Setup has been provided to identify approvers for this process. Once set up and enabled, notifications of proposed actions in the asset system will be delivered to the approver and be visible in a new list awaiting approval. Once approved the action will be released.
Enhancement | Added AppendToAssetItem field and AddToItemQuantity Boolean in Adjustment details tab of projectInterfacecontrol.Updated the AssetInterfaceAppend set action, AppendToReleasedAsset and AppendToUnreleasedAsset.
Enhancement | Previously only a full disposal could be reinstated. A partial disposal results in the disposed portion of an asset being split off into a new added which has a disposed status. This update will allow you to reinstate that portion of the asset. It will not be re-added to the original asset but be reinstated to a released status, create the necessary transactions to reverse out the disposal, and allow again be depreciated going forward.
Enhancement | When we perform ResetAdjustment, fields on Asset, AssetItem, AssetFunds, AssetItemFunds should be reset successfully. To track the Fund related adjustments added a link on AssetAdjustment, AssetItemAdjustment, where it shows the Audits for Fund record changes.
Enhancement | This enhance will add a new parameter to the asset company called append to path. This will control how asset interface records flow into the system when an 'Append To' asset is assigned to the project interface control record. This option will default to 'Item Adjustment Interface' which will push the new records, using existing functionality, to the asset item interface adjustment file. When the 'Asset Interface' option is selected, the newly added capitalization records will be added into the Asset Interface business class. These may be added to the append to asset individually using the append to (Un)Released Asset option or the new mass update action 'Asset Interface Append'
Enhancement | To improve user experience by adding call out actions and reducing number of clicks to complete a process, Improvements in alignment by rearranging and grouping of fields in each page. Providing inline create and initially display search wherever it is needed.
Enhancement | This enhancement involves developing a Top Tier page for the "Close Dashboard" for Monthly Processing in the Assets Webapp.
Issue | When we run AssetDepreciationCalculationandList with Excel as report option Asset number and total values are repeated. After changes values are not duplicated.
Enhancement | Application Administrators have been granted access to all available consolidated webapps as well as a new consolidated Administrator webapp that includes functionality from the original Application Administrator webapp. Financials Viewers have been granted access to all available financials consolidated webapps. Supply Management Administrators have been granted access to all available supply management consolidated webapps. Supply Management viewer will now have access to the Purchasing, Inventory, Item Lifecycle, Contracts, Sourcing, EDI, Work Order, Order Entry, Close, Warehouse, Kitchen Management, and Administrator webapps. The functionality of the consolidated webapps should include everything that was available in the original webapp.
Enhancement | Implementing AssetRegister report using Columnar to get better efficiency. Added aggregation tables in charts to check sums broken out via different variables. AssetBook now has InServiceYear and DerivedDepreciationRate derived fields. These fields are also now replicated in the AM replication set.
Enhancement | Added a parameter in AssetPeriodClose Report and AssetPeriodClose Online action.
Issue | Added logic for the Posting Date field on transactions resulting from Asset Interface processes so that the Asset Company posting date default options are applied.
Issue | An edit has been added which will prevent a user from personalizing the asset transaction and asset book transaction so that the amount of a system generated entry reflected in the asset book is not updateable. Adjustments to the item cost or and book amounts should be used to drive the creation of the appropriate transactions.
Issue | User will be able to reinstate a cancelled service PO invoice.
Enhancement | Added 2 boolean fields InterfaceUnrelasedReceivableInvoice and InterfaceUnreleasedPayablesInvoice in IntercompanyBillingDocumentHeader whose initial values are defaulted from InterfaceUnreleasedInvoices field from respective receivables and payables company. When the field is enabled then the respective invoices will be created in unreleased status else invoices will be created in released status which is an existing behaviour.
Enhancement | A new action has been added to Life Events called "Change Event Date" which will create a new Event on the date specified and inactivate the existing event.
Issue | On a create in ACA Covered Individual, the dependent search is titled "Dependents" and only includes dependents that have been identified as benefit eligible.
Enhancement | A email icon is now available for ACA integration which enables the setup of email notification parameters such as email recipient, subject and body. If email notification feature is configured and enabled, and a runtime issue occurs in ACA integration dashboard, an email notification will be sent to the designated recipients. In addition, a new action is available in Integration Maintenance > Actions, titled "Set Default Email Content". When triggered, this will populate the email subject and body with predefined content, should they be left blank.
Enhancement | This enhancement allows Benefits Admins to purge 1095-B/C Compliance Documents by year, ALE Member, Employee, or individually in order to allow customers to manage their own documents when creating them. This change also allows viewing of Compliance Documents for individual ACAIRS records, allowing easier access to purge Compliance Documents individually.
Enhancement | Lists and fields related to this project like Annual Deadline for ACA Delivery Method Changes, Standard 1095-B Template, Standard 1095-C Template, Alternative 1095-B Template, and Alternative 1095-C Template are added to the main tab in organization, and Email Automation tab is added to the same.
Enhancement | An Administrator can now run the "Remove Stop Date" action on an Employee Benefit record and it will attempt to remove the End date on this record and update/delete other related records that are tied to that End date.
Enhancement | The ability to adjust/setup the deduction start and deduction end within the plan contribution setup now exists.
Issue | When creating a new ACA offer, the end date is now calculated correctly if there are existing offers with future dates. Existing offers will also have their end dates adjusted accordingly.
Issue | The current maximum file limit will be updated to 100MB per file.
Issue | The current maximum file limit will be updated to 100MB per file.
Issue | Updated Add button to be visible on Beneficiaries in Dependents and Beneficiaries Section during Step Enrollment of Life Event or Open Enrollment.
Issue | Update Beneficiaries Button now only displays when Anytime Beneficiary Update is enabled in Benefit Plan Settings.
Issue | The currently enrolled plan will now match the same divisor as what the selected plan is set up to use to give a better comparison of the values in the Step Enrollment process.
Issue | Mass Create Eligibility Delete Report Option job does not fail with Async Errors if there are no Errors to Delete.
Enhancement | The change fixes the contents of Box 14 and Box 16 on the 1095-C forms from their detailed description to their value.
Issue | When step enrollment is enabled and enrolling dependents to a coverage, the select list will now only display the dependents eligible to be enrolled to the specific coverage of the benefit plan.
Issue | This change hides the Purge Compliance Documents action from unrelated forms and lists.
Enhancement | 1. Retain Zero Budget flag - This new flag, “Retain Zero Budget,” is available within the Budget Scenario. - The flag is displayed when the “Allow Zero Budget” flag is enabled. - When "Retain Zero Budget" is enabled, zero budgets are created and stored, and existing budgets updated to zero are retained. - When the flag is not enabled, zero budgets are not created, and existing budgets updated to zero are deleted. 2. Exporting Zero Budgets: - The “Export For Import” functionality now includes an option to export zero budgets, making it easier to manage and update zero budgets. 3. Budget Upload Message: When budgets are uploaded, the message “Budget upload in progress” will be displayed to easily monitor the upload's status. 4. A new Action Delete Zero Budget” is available to delete zero budgets as needed. 5. Security Class Modifications: The security classes have been modified to allow access to FINBudgetProcessing_ST and restrict access to GLAdditionalProcessing_ST for the "Delete Zero Budget" action.
Issue | Changing the post date to a different year on an invoice with budget edit errors will reevaluate the budget errors
Enhancement | If a document does not have distributions enabled for budget editing, it will not be budget edited and will not be added to the Budget Edit Queue. However, if a document has at least one distribution enabled for budget editing, it will go through the budget editing process and will be added to the Budget Edit Queue.
Enhancement | This list shows the business classes that were changed: modules/cb/bl/CashLedgerTransactionImport.busclass modules/cb/ui/CashLedgerTransactionImport.busclass
Issue | The Rule which requires a nonzero Amount has added a criterion, such that if the Units Amount is nonzero, no error is created. The Rule is updated in CashLedgerPaymentImport, CashLedgerReceiptImport, and CashLedgerTransactionImport busclasses.
Enhancement | When approving salary awards on Administrator > Compensation > Awarding > Awarding Process > Roll Up Approval Views, if the work assignment for the employee found in the Employee Salary Planning is inactive, an error message appears showing which Employee and Work Assignment are inactive.
Enhancement | Changes have been made to allow for the return of a Job Code as a method to identify "Other Rates of Pay" for an employee.
Enhancement | A set action is created on the Step and Grade schedule business class which will loop through active Step and Grade schedules and trigger an update action on Work Assignments not in-sync with the Step and Grade schedule.
Issue | The final approval errors for the Compensation Program Approval were caused by an additional quotation mark in the Final Approval LM node's _authenticatedUser, resulting in formatting issues. By removing the extra quotation mark, final approvers can now proceed with the approval process without encountering errors.
Enhancement | A confirmation message will be displayed when the user entered a Pay Rate that is not within the selected Salary Structure Grade.
Enhancement | A confirmation message will be displayed when the user entered a Pay Rate that is not within the selected Salary Structure Grade.
Enhancement | With this change, the changes in the Work Assignment tab will also be seen in the "At a Glance" link even if the change only exists in the Work Assignment tab.
Enhancement | Admin, Generalist, CompensationAnalyst and ActorOrgUnitCompensationAnalyst will have access to consolidated compensation webapp when feature toggle is enabled.
Enhancement | Admin, Generalist, CompensationAnalyst and ActorOrgUnitCompensationAnalyst will have access to consolidated compensation webapp when feature toggle is enabled.
Enhancement | Supervisors can see their indirect subordinates' action requests and work units in the "Approval Tracking" tab of "My Staff" page. Additionally, it will enhance security of subordinates' work units from indirect or non-indirect supervisors.
Enhancement | GL lists have new default filter operators that either use starts with or equals to improve performance.
Enhancement | A Utility that rebuilds commitments and encumbrances scenario records in GeneralLedgerTotal from released GLCommit records. The Utility clears GL Totals by system and rebuilds the GeneralLedgerTotal using the sum of the linked GLCommit. It rebuilds totals from the sum of encumbrance or commitment transactions or both based on input.
Enhancement | modules/GeneralLedger/bl/GeneralLedgerJournalComment.busclass
Enhancement | modules/GeneralLedger/ui/FinanceEnterpriseGroup.busclass
Enhancement | The pivot list will show GL totals of commitments, encumbrances, the total of both, and year-to-date variations. It includes two period views of Month and Quarter.
Enhancement | In the Allocation Control, a new tab "Journal Transaction Description" was added to allow users to select combinations of Allocation Name, Allocation Description, Allocation Line Name, and Allocation Line Description flags. The selected Allocation information will form the journal transaction description for the journalized allocation transactions.
Enhancement | The new "Overthrown Amount Option" was added in the Main tab of the Allocation and in the Allocation Options section of the Allocation Line. In the Allocation, you can select whether to allocate the overthrown amount to the "Last Transaction" or the "Last Highest Weight". In the Allocation Line, you can select "Default From Allocation" to inherit the Overthrown Amount Option setting in the Allocation. Select "Last Transaction" or "Last Highest Weight" to override the value of the Allocation.
Enhancement | 1. Callout search option on AccountingEntityPeriod modules/GeneralLedger/ui/AccountingEntityPeriod.busclass 2. Call out search option for GeneralLedgerCompanyGroup, GeneralLedgerCompanyGroupMember, AccountingEntityGroup, LedgerBasisGroup and LedgerBasisGroupMember modules/GeneralLedger/ui/AccountingEntityGroup.busclass modules/GeneralLedger/ui/LedgerBasisGroup.busclass modules/GeneralLedger/ui/LedgerBasisGroupMember.busclass modules/glif/ui/GeneralLedgerCompanyGroup.busclass modules/glif/ui/GeneralLedgerCompanyGroupMember.busclass 3. Call out search option on RecurringJournalControl modules/GeneralLedger/ui/RecurringJournalControl.busclass 4. Call out search option on ReportingBasis modules/GeneralLedger/ui/ReportingBasis.busclass 5. Callout search option for FinanceDimension2 modules/GeneralLedger/ui/FinanceDimension2.busclass
Enhancement | 1.Warning messages while deleting the Structure from FD1 to FD5. modules/GeneralLedger/bl/FinanceDimension1Structure.busclass modules/GeneralLedger/bl/FinanceDimension2Structure.busclass modules/GeneralLedger/bl/FinanceDimension3Structure.busclass modules/GeneralLedger/bl/FinanceDimension4Structure.busclass modules/GeneralLedger/bl/FinanceDimension5Structure.busclass 2.Warning messages while deleting the Structure from FD6 to FD10. modules/GeneralLedger/bl/FinanceDimension6Structure.busclass modules/GeneralLedger/bl/FinanceDimension7Structure.busclass modules/GeneralLedger/bl/FinanceDimension8Structure.busclass modules/GeneralLedger/bl/FinanceDimension9Structure.busclass modules/GeneralLedger/bl/FinanceDimension10Structure.busclass 3.Warning messages while deleting the Structure on AccountingUnitStructure. modules/GeneralLedger/bl/AccountingUnitStructure.busclass
Enhancement | 1. Remove the delete icon and show delete option in the Ellipses, change it in FD2 to FD6 modules/GeneralLedger/ui/FinanceDimension2Structure.busclass modules/GeneralLedger/ui/FinanceDimension3Structure.busclass modules/GeneralLedger/ui/FinanceDimension4Structure.busclass modules/GeneralLedger/ui/FinanceDimension5Structure.busclass modules/GeneralLedger/ui/FinanceDimension6Structure.busclass 2.Remove the delete icon and show delete option in the Ellipses, change it in FD7 to FD10. modules/GeneralLedger/ui/FinanceDimension7Structure.busclass modules/GeneralLedger/ui/FinanceDimension8Structure.busclass modules/GeneralLedger/ui/FinanceDimension9Structure.busclass modules/GeneralLedger/ui/FinanceDimension10Structure.busclass
Enhancement | 1.Modify the Warning message while deleting the Posting Dimension in the Finance Dimension Structure Hierarchy for FD1 to FD5. modules/GeneralLedger/bl/FinanceDimension1.busclass modules/GeneralLedger/bl/FinanceDimension2.busclass modules/GeneralLedger/bl/FinanceDimension3.busclass modules/GeneralLedger/bl/FinanceDimension4.busclass modules/GeneralLedger/bl/FinanceDimension5.busclass 2.Modify the Warning message while deleting the Posting Dimension in the Finance Dimension Structure Hierarchy for FD6 to FD10. modules/GeneralLedger/bl/FinanceDimension6.busclass modules/GeneralLedger/bl/FinanceDimension7.busclass modules/GeneralLedger/bl/FinanceDimension8.busclass modules/GeneralLedger/bl/FinanceDimension9.busclass modules/GeneralLedger/bl/FinanceDimension10.busclass
Enhancement | Added four lists in panels to better distinguish close status by ledger. Added two card view lists that include a current period list by ledger and a card view list by open and backpost. Two new panels with Limited and Final close status lists. Added called out actions for easier processing.
Enhancement | Added list group labeling to the multi-list page and updated the panel's labeling. Added commitment and encumbrance list to Document form.
Enhancement | Added empty state messages and updated titles and labels to better accurately describe lists and forms used in the Journal Control form.
Issue | This list shows the business classes that were changed: modules/GeneralLedger/bl/GeneralLedgerChartAccount.busclass modules/GeneralLedger/bl/GeneralLedgerTransaction.busclass modules/GeneralLedger/ui/GeneralLedgerChartAccount.busclass Instead of loading transaction through GeneralLedgerTotals now transactions directly loading from GeneralLedgerTransaction.
Issue | Security conditions were defined in a way that resulted in slow database queries. These are fixed to prevent database post-processing.
Issue | Move action is made as hidden across the accounting entity
Enhancement | There is a request to capture a cross-dimensional area of responsibility. For example, a user may be an approver or responsible for a department within FinanceDimension1 but only for a specific value in FinanceDimension3. Adding the ability to create a custom-defined code block for evaluating distributions to route it to the appropriate approver in general ledger.
Enhancement | The Purge Transaction Detail action is enhanced to offer a Include Project Records In Purge parameter to control whether records that have Project set should be purged.
Issue | Post Through Date parameter should only apply to Journal Control's posting date. Removed Post Through Date as a criteria when selecting the transaction for posting in GeneralLedgerTransaction.
Issue | Added context to the field label for the Post Journal form to accurately display label.
Issue | This list shows the business classes that were changed: modules/GeneralLedger/bl/GLTransactionInterface.busclass
Issue | Set effective date as of current date before sending email for current employee information in an email
Issue | In L&D admin, under catalog -> activities and sessions -> open an activity -> outcomes -> now the L&D admin has the option to delete the outcomes. Similarly, L&D admin can delete the skills and credentials as well.
Enhancement | Evaluations are no longer assigned to the Employees when their Activity Enrollment are Waived, Cancelled, Rejected, and Withdrawn.
Enhancement | For Email Notifications which are made active for a Transition Management Program Task with an associated Learning and Development component, the Transition Management Email Notifications will continue to execute while the corresponding related Learning and Development Email Notification tied to the component will not execute, avoiding duplicate emails.
Issue | The Assign Checklist and Enroll in Activity actions are no longer available on the lists in the Birthdays and Anniversaries page.
Issue | Employees are now prompted to complete or request to waive the prerequisites when enrolling through a development plan.
Issue | In order for the Transition Program Learning Activity Task due date to be consistent with the new due date set on the Learning Activity enrollment, if the Transition Task has no due date and the Transition Program has a due date, this due date will now be leveraged on the Transition Task, as well as the Learning Activity enrollment.
Enhancement | Learning Administrator can now set up notifications which are being received by employees when their enrollment in Activities, Development Plans and Certifications are waived. A default template for Activity, Development Plan and Certification Enrollment Waived can be uploaded in the L&D application through Delivered Content and can be used as template when notification is set up. The notification for Activity, Development Plan and Certification Enrollment Waived can be set up both in Default Notification Rules and in Notifications tab which can be found under a specific Activity, Development Plan and Certification.
Issue | On L&D scheduled notifications action forms, the description will now be enclosed in parentheses.
Issue | Change complete learning session date field to the correct timestamp
Enhancement | A learning administrator enables employees to become content authors, which allows them to upload content. Once the content is uploaded, it will send a notification to the learning administrator. If a learning administrator approves the request an activity will be created and it will be available in the catalog for employees.
Enhancement | Employees are now redirected back to their Development Plan after marking the Activity as complete, after Online Content in the Activity has been completed or after the Activity with post-test has been finished.
Enhancement | Learning Administrator and Instructor can use the send email option on the Session Registrations screen within a Session to send an email to a selected or all the participants with confirmed registration.
Enhancement | A learning administrator enables employees to become content authors, which allows them to upload content. Once the content is uploaded, it will send a notification to the learning administrator. If a learning administrator approves the request an activity will be created and it will be available in the catalog for employees.
Enhancement | A learning administrator enables employees to become content authors, which allows them to upload content. Once the content is uploaded, it will send a notification to the learning administrator. If a learning administrator approves the request an activity will be created and it will be available in the catalog for employees.
Enhancement | As an L&D Admin, When I navigate to Setup > Evaluation components > Evaluation Forms >Forms. While creating a form and selecting a section with type question the duplication selection of the section with same name has been restricted so that the customer can avoid the duplication of question in the same evaluation form
Issue | The Column Heading "Date Completed" now displays in the Past Activities list.
Enhancement | A Post Upgrade Action Populate Activity Instructors for existing Learning Sessions is being introduced as a part of this enhancement. This process will populate Activity Instructors for existing Sessions with assigned session Instructors. This upgrade will run automatically during delivery of this CU. Note: All records in the system related to this upgrade process will be evaluated and those that are updated will include a new Update Time Stamp. As a Learning Administrator, Local Learning Administrator, Content Administrator or Instructor Instructors can be added to an Activity in the Activity > Instructors and Content Admins panel > new Instructors list. If open Sessions exist with no Session Instructor, a toggle for assigning to all open Sessions with no Instructor will appear and if enabled, the Activity Instructor will get assigned to the open Sessions as Primary type as well as the Sessions Classes. Opening an Activity Instructor record will provide a view of all Sessions where the Instructor is assigned within the Activity. Additionally, Instructors may now be added to a Session during the Create Open Session action, using the new Instructor fields on the action form.
Enhancement | Learning Administrator can now add different providers as part of the Activity Components. They can also define the source of the activity's provider (External or Internal). For third-party content provider integrations, such as LinkedIn Learning and OpenSesame, a post-upgrade action is now available to add these providers in the Provider field, as well as to update the existing records with the correct provider value. The Provider field has also been added to the sync content provider catalog pages to ensure that the correct values are populated in the Activities after the sync.
Enhancement | Employees and External Learners can now take their Post Test when they have finished their CMI5 Online Content. The Activity will now not be complete unless the Post Tests are completed.
Enhancement | Learning Administrator,Local Learning Adminstrator and Instructor can now enroll and register multiple employees to Development plans using the Add Multiple action. External Learner Administrator can now enroll multiple External Learners to Development Plans using the Add Multiple action.
Enhancement | Learning Administrator, Local Learning Administrator and Instructor can now enroll and register multiple employees to Certification using the Add Multiple action. External Learner Administrator can now enroll multiple External Learners to Certification using the Add Multiple action.
Enhancement | Employees will not receive Waived Certification notifications from an Inactive version of a Certification during the activation of a new Certificate version.
Enhancement | As an Employee I can now see a display image for Activities, Development Plans Certifications and checklist and also will see launch button so that employee can launch the online content for the activities which make easy process for the employees
Issue | Employee can use the Copy My Activity action to create a new personal activity for an existing personal activity
Enhancement | The Approver dropdown field should provide the following options: Manager, Learning Administrator, and both. Depending on the selected approver, the responsibility for approving the employee's enrollment in the activity will fall to the chosen individual. This ensures that the appropriate authority validates and endorses the employee's enrollment in the specified activity.
Enhancement | Allow Manager or Learning Administrator to manage session registration requests
Issue | Now when the L&D admin enrolling employees to development plans or certifications. the FromMassAssign field will now be correctly populated.
Issue | The employee will now be redirected back to the Employee Activity Details page after selecting the "Return to Learning and Development" button.
Issue | Applied a limitation wherein an activity will not be auto enrolled when the next Activity has a conflict on the Order of Completion.
Enhancement | This change will provide the HR Generalist with HRGeneralistActorUnitAccessLevel_ST role with access to L&D setup, inquiry and other actions.
Enhancement | Allow Manager or Learning Administrator to manage Activity Enrollment Requests that has a prerequisite
Enhancement | A learning administrator enables employees to become content authors, which allows them to upload content. Once the content is uploaded, it will send a notification to the learning administrator. If a learning administrator approves the request an activity will be created and it will be available in the catalog for employees.
Enhancement | A reason should be required when a Learning Administrator rejects an activity and session enrollment request
Issue | The issue is now resolved by updating the last class date and time to match the most recent session update. The L&D admin can complete the session if it occurs on or after the last class date.
Enhancement | In the new Occupational Health consolidated web application, the action Assign Health Components by Eligibility Group has now been added for health facility managers.
Enhancement | In this action, records related to Employee Safety will be removed in the database. Users can create custom groups which will allow them to select the records that will be affected by the “Purge Employee Safety” action.
Enhancement | Records related to Occupational Health will be removed in the database. Users can create custom groups which will allow them to filter records that will be affected by “Purge Occupational Health” action.
Issue | Report Covid-19 Incident action is now available when enabled in the Revised Employee Experience.
Enhancement | A new configuration option exists in organization setup that will enforce the legal entity be kept in sync with the organization unit on the work assignment. The customer must opt in and select the "Update Legal Entity to Organization Unit" feature in organization setup, otherwise there will be no change to the current defaulting and processing.
Enhancement | Administrator or HR Generalist will be able to update Due Date using Update Appraisal Period action. On the Update Appraisal Period action we have now added Due Date as an option.
Enhancement | We added new template to send automatic email notification when appraisal that were in 'Ready For Review' or 'Submitted For Review' are being reverted to in-progress
Enhancement | Administrators and HR Generalists can now send reminders for overdue appraisals. The action is available Administration => Performance => Create Appraisal Reminders => Overdue action.
Enhancement | Manager will now be able to create appraisal only for primary work assignment.
Enhancement | Previously blank name was being displayed, we now enhanced this feature which will replace blank name with 'Anonymous'
Issue | Added the display of the instructions to the header section of the employee appraisal consolidated pdf when the “Appraisal Form Instructions” is set on the Appraisal Form setup.
Enhancement | We now have added Meeting Date option when appraisal is submitted by manager from entry form
Enhancement | Add Minimum to Bill for Project Invoicing. Add field for Invoice Minimum at the Project funding source and the Project Funding Source Template. Invoices are generated as before, but at the end of the action each one is checked to verify that the total amount meets the minimum invoice amount (if any) on the associated funding source. If any invoice fails to meet the minimum, it will then be automatically deleted. If it is a multi-funded contract, partially billed transaction entries may be generated for any expenses that were split between an invoice that failed to meet the minimum and one that succeeded (or had no minimum).
Enhancement | Added ability to invoice a single posting project per invoice. Added ability to bill posting projects on separate invoice in same invoice run. Single Project Invoices and Single Revenue Recognition fields have been added to the project contract. When enabled, Generating invoices and/or Recognizing Revenue actions will create a single invoice/revenue group for each posting project and funding source.
Enhancement | Enhance the Recognize Revenue and Generate Invoices actions to populate the GLTransaction.Description with the GLTransaction.Reference. Fill the description field with whatever we are currently moving to the reference field so customers can filter in their 3rd party reporting tool.
Enhancement | Add new business class to create relationship between FD2 and posting projects. While this relationship is primarily used for SEFA reporting the relationship is on all funding source types. Posting projects can be added individually by using the Create action or multiple can be added using the helper list. Add the related funding source field to the posting project. If project is single funded, adding the related FD2 to the posting project will allow the ability to include FD2 and related grant attributes to project reports.
Issue | Both the prime sponsor and receivables customer fields should be visible and enterable on the grant reporting tab for external grant type funding sources.
Enhancement | In order to eliminate the 19999 transaction limit for invoicing and revenue, a “temporary” table named ProjectInvoiceTransaction has been added. This is loaded with qualified GLTransactionDetail records, then read in transaction date order (credits first) as input to the calculation routines. Important information: Any pre-existing invoices or revenue in draft status will display a zero amount on the top list until they are journalized because the derived field definition was changed to reflect the fact that the new version updates totals at creation time instead of journalize time. When “old” draft records are journalized, the totals will be updated at that time.
Enhancement | Add a mass action to update active ProjectContractFee rates. Add parameters including contract group, fee code, fee type effective date, and rate or percent. This action will not include tiered rates or percent. Also add a Project Contract Fee list to include all fees for all contracts. The list is a tab on the Contracts menu option for Project Administrator, Project Accountant and Projects roles.
Enhancement | Add type and funding source hyper link to deliverables and expiring deliverables lists.
Enhancement | Add a new partial revenue code block to FD3 and FD4 (and their respective uploads). Whichever of those has been designated as the Billing Override Level on the FEG is the one that will be used. The defaulting scheme used by invoice/revenue validation and journalization to build a code block from partial code blocks will now work as follows: The code block from the originating transaction is loaded. *If a ProjectBillingOverride record is found that includes a partial revenue code block, any entered components will be taken from it and the scheme is ended. *If the Project record includes a partial revenue code block, any entered components will be taken from it and the scheme is ended. *If a FD3/FD4 record is found that includes a partial revenue code block, any entered components will be taken from it. However the scheme is not ended. *If the ProjectFundingSource includes a partial revenue code block, any entered components that weren’t filled in from FD3/FD4 will be taken from it and the scheme is ended. The scheme for full revenue code blocks is unchanged. The order of defaulting is ProjectBillingOverride, then Project, then ProjectFundingSource.
Enhancement | Add a mass action to inactivate or activate ProjectContractFee rates. Add parameters including contract group, fee code, effective date (start and through), and status. The action is a called out action on the Contracts menu Project Contract Fees list for Project Administrator, Project Accountant and Projects roles.
Enhancement | The Generate Indirect Burden action will create two separate actions for each included posting project. The first action will generate the new workfile and the 2nd will process that data and create the ProjectIndirectBurdenTransaction records. These actions will run consecutively and can’t be multi-threaded.
Issue | The "NP" Global Ledger Event has been created for Non AR Payments. Before the Update Event Codes action is run on the Finance Enterprise Group, the "RP" Global Ledger Event will still be used. After the Update Event Codes action is run on the Finance Enterprise Group, the "NP" Global Ledger Event will be used. If a new Finance Enterprise Group is created, the "NP" Global Ledger Event will be used. Projects will include NP event codes to view unbilled lists and allow invoicing.
Enhancement | The Generate Indirect Burden action will create two separate actions for each included posting project. The first action will generate the new workfile and the 2nd will process that data and create the ProjectIndirectBurdenTransaction records. These actions will run consecutively and can’t be multi-threaded.
Issue | Project Amount Analysis YTD to update to be year to date totals for the period and year selected. It was keeping the same YTD amount no matter the period for the year.
Enhancement | Rewrite the project structure validation actions in labor distribution, invoicing and revenue, and indirect burdens to eliminate the 999 code block combinations limit. Added a new “temporary” database table named ProjectStructureValidationLine.
Enhancement | Performance enhancements for invoicing and revenue is to remove the 1000 codeblock limit for fund accounting, revenue summarization, and historical receivable distribution creation when journalizing. This will require the addition of a new “temporary” table to the database.
Enhancement | Add Project to the Contracts menu under Project Contracts. Add to all project roles.
Enhancement | Change Validation Errors menu name to Validation Results. Change on Errors tab for Invoicing and Revenue and Grant Labor Distribution Errors tab. Change on Projects, Project Admin role, Project Accountant role.
Enhancement | When fund accounting is enabled, you will see create cash offsets to the parameters to project contract FES Reverse and Reallocation and FES distribution jobs. This allows for those transactions to move from one fund to another without zone balancing occurring.
Issue | Auto-reverse flag to be removed on transactions that are reversed and reallocated in the project's module. When the Reverse and Reallocate action is run in project contracts, any original transactions with the auto reverse flag +Yes, the reverse and reallocate transactions will be created with the auto reverse = No.
Issue | Added an error handling when closing Procurement Card Statement Charge that Invoice should be released first
Enhancement | Employee Bank Detail Errors is a new operational report displaying the Employee Bank Detail Errors and the corresponding Employee Bank Detail information. The build action of "Build Employee Bank Detail Errors" was created as a call out action within the report. This is a prerequisite action to generate the data for the report. The identified errors generated by the report are as follows: NonDefaultAccountsGreaterThan100%, DefaultAccountMustBeTheGreatest_Distribution_Order. and Flat_AmountGreaterThan0AndPercent(s)=100% The report is accessible for Administrator, Payroll Administrator, HRGeneralist, and HRGeneralistActorOrgUnit. When displaying the report for HRGeneralist and HRGeneralistActorOrgUnit. The last 4-digit number of the Account Numbers and International Bank Account Number will be displayed while its preceding numbers are masked.
Enhancement | A new report named Employee Bank Details is available in the Report Catalog under Payroll > General > Employee Bank Details. This report will display all employee bank details. The Direct Deposit Information column contains a clickable link that will provide direct deposit information details of an employee. Payroll must be enabled in Organization configuration under Global HR Modules to make the report accessible to the users. This report can be viewed by Payroll Administrator.
Issue | When Year-End Compliance Documents are generated, if the Employee has multiple Sequence Numbers under the Employer Header, multiple Compliance Documents will be generated for the Employee.
Enhancement | Conditional Questions can be attached to Sourcing Events and Event Lines. Depending on how a Supplier responds to a question, different additional questions can be generated. Conditional Questions need to be set in the Repository Questions.
Issue | Removed passing of Dropship name and address when creating Vendor Return from Buyer Message
Issue | Remove flag initialization, then tolarance setup will be considered only if Cancel Backorder is false
Enhancement | Contract Attachments and Contract Comments are copied from Service Contract to the invoice when the invoice is matched with the Service Contract.
Enhancement | "Added new field ""Cycle Count"" flag in Manage Select IDs and ""Last Cycle Count Date"" in Item Location. Created new header ""Physical Inventory"" in Item Location to display related fields."
Issue | Passing of Write Off Quantity from Receipt Adjustment to Purchase Order Line when Purchase Order has Matched Quantity and adjust with negative value with Write Off = Yes. Creation of Inventory Transaction Line Distribution when Write Off Quantity occurs in Receipt Adjustment
Issue | To not have errors when password requirements are not met, made the process of Registration one step - enter required fields and save the record. Then status information will display about what is required. As requirements are met, status information will change. Registration tab will redisplay with text indicating what needs to be done next. Each tab will display with an asterisk to indicate data has been entered. Questions can be answered using a button.
Enhancement | 1. Added "display as required" in UI for fields with the required state in Requester Profile and Inventory Company. 2. Added value validation in the Action, Parameter, and Field rules when not entered.
Enhancement | Renaming of lists and panels: List: - Unreleased Inventory Transaction - Items with Zero Stock on Hand - Inventory Issues List Panel: - Procurement Expense Summary - Procurement Expense Details Added initial display search - Enter Counts Modify empty messages - Returns - Transfer Receipts
Enhancement | added empty state messages added group labels and labels modify and added action form labels renamed list and panel titles
Enhancement | In the PO Line Dashboard -resized and reordered the widgets -Applied Cardview hierarchy on the Purchase Order Line Dashboard widgets -Updated List Title, field labels, group labels, labelfields -created condition to hide OtherVendor field in AddOnCharges widget created overview navigation for the following widgets and their destination lists/forms Receipts > Purchase Order Receipt Line List Invoices Details > Invoice Details For A PO Line List Receipt Adjustments > Receipt Adjustment Line Detail List Receiving Buyer Messages > Receiving Buyer Messages List Source Lines > Purchase Order Line Sources panel Distributions > Purchase Order Line Distributions panel Add On Charges > Purchase Order Line Add On Charges panel Inspections > Receipt Inspection Lines List VendorReturns > Lines For PO Dashboard List
Issue | For a Contract Line that has been converted from Special to Itemmast, no error is received regarding UOM conversion if the Contract Line UOM is changed.
Enhancement | The 'Infor' provided data from this enhancement include: -> Action Event Messages setup screens for all actions involving the Source to Settle process -> JSON UserTemplates for each business class used in the Source to Settle process
Enhancement | Item can now be searched separately on the Contract Lines search
Issue | The proper contracts will now display on the page associated with My Contracts
Issue | Awards will be allowed for event lines that have responses which are only for alternates.
Enhancement | Will give users the ability to evaluate (score) contracts as pertained to the respective user. Very similar to how users are able to evaluate a supplier with a supplier evaluation, this will be the same thing but just with contracts instead.
Issue | Suppliers are able to search on Types and Categories for Events Security changes to SupplierAnonymousViewAndRegister_ST and SupplierSharedInformation_ST
Enhancement | Historically, the fourth element of N1 segment with an ST qualifier contains the "shipto account number". the account number is sent in the 850 and it is expected to be returned in an N1ST in the documents from the vendor. This account number is used to cross-reference with company, vendor, ship to location, etc. When using Global Location Numbers (GLNs), there is a unique identifier for company, vendor, location assigned by the "owner" of those entities. account numbers are not used. The EDI application expected the documents from the vendor to include either an account number in N1ST or N1 segments with specific GLNS. It did not handle scenario where vendor sent N1ST with a shipto GLN and an N1BT with an account number. This enhancement enables using other N1 segments to cross-reference company or vendor. If N1 segment has a "BT" qualifier and company value is not set, the N104 value will be used for the I_COMPANY lookup. using this data as example N1^BT^INFOR^91^11157439~ N1^RI^JOHNSON CREEK, INC~ N1^SE^^92^944630~ N1^ST^INFOR HOSPITAL^UL^1100004921369~ The "11157439" in the N1BT segment will be used to lookup the company. The GLN in the N1ST segment is mapped to the Ship To Location Global Location Number field.
Issue | Q and A and Question records can now be opened to view quesion or answer text (for Q and A).
Enhancement | For Contracts, when a Structure Relation is set up for Project to Fund, the default fund will default to the contract line distribution. It will also work for the Default Account from contract header and on contract line creation for Default Account. The defaulting and editing should also now be available for Requisition Header Defaults.
Issue | The receipt interface will provide a way to change the line number on a receipt line, and also provide useful lists of the related PO lines
Enhancement | Implemented the attachment list to Requisition Self Service LPL screens for requisition header and line comments.
Issue | For Action History panels provided a printable format by removing any process indicators and changing the User Action Routing list from an HTML model to a list that displays correctly. This was done for the following business classes: BankStatement CashForecast CashLedgerBatchApproval CashLedgerCashReceiptHeader CashLedgerElectronicFundsTransferTranscation CashLedgerPayablesPayment CashLedgerReturnedPayment CashLedgerTranscation Contract PurchaseOrder Supplier RecallNotice Requisition RequisitionLine SourcingEvent
Issue | Added a condition, if the comment type from the Requisition Line is "Display Only", it should not create Line comment for the Purchase Order
Issue | 1.Remove the constraint that requires Requesting Location and Operating Company to be entered when Source Document is entered 2. Don't show the Operating Company and Requesting Location as required when Source Document is entered.
Issue | Text fields are able to be fully viewed for Links and Instructions on home page, Q and A, Comments, Meetings, Questions, and Amendments in Event information, and Comments, Questions, and Attachments in Event Line information.
Issue | Valid UOMs are visible when doing a select on Supplier Portal - Line Responses - Entering Alternate Response
Enhancement | Currently, when you need to upload multiple attachments, you need to create one comment record at a time (header and line comment). This functionality will allow you to create multiple comment records by selecting up to 5 attachments in a single action (header and line)
Issue | In VendorReturnLine, modified the existing condition for the creation of VendorReturnLineDetail if ItemLocation is not Bin Tracked.
Issue | The issue has been fixed by adding a checking for the Requesting Location, whether it is a Par Location or not, since this checking is necessary before passing the vendor value used when checking available contract lines for the item in the cost defaulting routine.
Issue | All Itemmast Contract Lines with either a UOM that is not the Stock UOM or is the Stock UOM and that have a UOM Conversion on Item will have a value in the Contract LIne > UOM Conversion field that is not 1
Issue | 1. The LineFullyCancelled condition was modified where in we added that it will satisfy the condition when ServiceCancelAmount = EnteredUnitCost and ServiceCancelAmount is entered. 2. A new messagefield was added. It will show, "Cost to be determined" if the cost option is Vendor Determined and there's no entered unit cost. And "No charge item" if the cost option is No Charge in the PO Document.
Enhancement | This new report will be available to Administrator, HRGeneralist, and HRGeneralistActorOrgUnit users. Missing FTE On Primary Work Assignments report will display active employees where FTE is not stated on their primary work assignment. It will have the employees' basic information and a link pointing to the Compensation form to view the employee profile. Retired With No Termination Date report will display retired employees with no termination date stated in their profile. It will have the employees' basic information and a link pointing to the Dates form to view the employee profile. Missing Work Assignment report will display all the active employees with missing primary work assignment or no work assignment in their records. It will have the employees' basic information and a link pointing to the work assignment records.
Enhancement | A new columnar report named Active Position Vacancy is available in the Report Catalog under HR Administration > General > Position Vacancy. This report displays active positions with no attached active work assignments. The feature toggle, Columnar Reports Oct 23 CU, Apr 24 CU and Oct 24 CU Releases, must be enabled. This report can be viewed by Administrator, HRGeneralist, and HRGeneralistActorOrgUnit.
Enhancement | A new option has been added to the Turnover tab on the Organization setup called 'Configure Turnover By Dates'. When this setting is selected, the landmark turnover reporting action will make use of the turnover calculation settings on that tab and the turnover data list will also display a new list relevant to these settings.
Enhancement | There are new settings on the HROrganization for controlling how the turnover report is calculated. A new dashboard has been created for this new functionality. This dashboard is found under Report Catalog -> HR Administration -> Turnover -> Turnover Analysis
Issue | Since we have changed the trial period end date for the Report Catalog to a later date, we have changed the behavior of the toggle for the new App Navigation feature.
Enhancement | Similar with 'List' type questions, 'Multi-select' questions can now be tagged as a 'Requirement Question' while 'Requirement Type' can be selected for each 'Answer'. Configured 'Multi-select' requirement questions will be part of the calculation for 'Meets and Exceeds'.
Enhancement | When attaching a candidate to a requisition, the 'Use application date from another application' checkbox can be utilized. When enabled, the recruiter needs to select the source of the application date from the list of the candidate's active applications. On both 'Attach Candidate' forms, additional data fields are only displayed when corresponding checkboxes are enabled. (Ex. Email fields are only displayed when 'Notify by email' is enabled')
Enhancement | When the initiator enables the Inbox summary feature toggle and performs the ‘Hire’ action on the candidate, the approver should be able to see the summary tab in their inbox message with all the required fields, icons, and descriptions.
Enhancement | When the initiator enables the Inbox summary feature toggle and performs the ‘Rehire’ action on the candidate, the approver should be able to see the summary tab in their inbox message with all the required fields, icons, and descriptions.
Enhancement | When the initiator enables the Inbox summary feature toggle and performs the ‘Transfer’ action on the candidate, the approver should be able to see the summary tab in their inbox message with all the required fields, icons, and descriptions.
Enhancement | When the initiator enables the Inbox summary feature toggle and performs the ‘Promote’ action on the candidate, the approver should be able to see the summary tab in their inbox message with all the required fields, icons, and descriptions.
Enhancement | When the initiator enables the Inbox summary feature toggle and performs the ‘Add Assignment’ action on the candidate, the approver should be able to see the summary tab in their inbox message with all the required fields, icons, and descriptions.
Enhancement | When the initiator enables the Inbox summary feature toggle and performs the ‘Define Offer’ action on the candidate, the approver should be able to see the summary tab in their inbox message with all the required fields, icons, and descriptions.
Enhancement | When the initiator enables the Inbox summary feature toggle and performs the ‘Request to Update Requisition’ action on the candidate, the approver should be able to see the summary tab in their inbox message with all the required fields, icons, and descriptions.
Enhancement | Additional columns were added to Employee With Allowances, Employee With Alternate Pay Rates, and Other Pay Rate Audit reports to support information on columns that only displays numerical values. The new column named Issue(s) will help users to identify if there are mismatches between the employee's information and the Criteria Fields from Allowance/Alternate Pay Rate/Other Pay Rate Information. This can be accessed by Administrator, HRGeneralist, or HRGeneralistActorOrgUnit.
Enhancement | A new Span of Control list will be added in Rebuild Maintenance menu. The existing Span of Control set up screen will be maintained yet, the option to process the action will be moved to the new Span of Control screen. Once this enhancement has been applied, the old "RebuildSpanofControl" action in Action Configuration will no longer be available and will be replaced with "ProcessSpanOfControl". The old thread count will be copied over to the new thread during the update process. Existing Span of Control rebuild schedule should be working as it is.
Issue | For an employee with only a Flat amount Bank Details record, the check type will be set to System on a zero net check payment.
Enhancement | In the Action Configuration, number of threads can now be defined under RebuildSpanOfControl action.
Enhancement | There are three setups available to handle bank account information. These are: No Validation - Accuity is not used in this setup. Any details that will be entered in adding bank account information will be accepted. Warning - Accuity will determine if bank account information entered is valid. If it's not valid, user will be prompted that they can still proceed in adding bank account. The bank account will be tagged as unverified. Error - Accuity will determine if bank account information entered is valid. User cannot proceed in submitting the bank account if Accuity cannot verify the bank account details. Aside IBAN, Accuity validation is also applicable for countries that are using SWIFT/BIC or Routing Number in domestic/international transactions. We're currently supporting 87 countries for bank account validation. Setup of these countries will be part of the delivered content included in the enhancement.
Enhancement | Thumbnail images were added to the lists of documents in Health and Safety module.
Issue | Wage Analysis report compares the current and prior pay periods of an employee, based on hours and total gross/net amount earned, to provide reasonability and verify there are no extraneous hours or bonuses. Deductions Not Taken report identifies scheduled deductions or one-time deductions that were not included during payroll processing. Employee Payment information containing relevant deduction and payment information is also displayed. This can be accessed by Payroll Administrator.
Issue | Added on a new UI element to Employee Deduction that is display only for the custom tax provider code
Enhancement | The new action can only be used when "Configure Turnover by Dates" is enabled. 1. The action will be used to create turnover data when "Configure Turnover by Dates" is enabled on the turnover tab via Administrator> Setup>Structure>Organizations> Select your organization. 2. Once "Configure Turnover by Dates" is enabled, the action of Create/Update Data in Turnover Reports, will display via Administrator> Report Catalog> Turnover>Turnover Analysis>Overview. 3. The existing turnover action will be in used if "Configure Turnover by Dates" is NOT enabled.
Enhancement | A new option has been added to the Turnover tab on the Organization setup called 'Configure Turnover By Dates'. When this setting is selected, the landmark turnover reporting action will make use of the turnover calculation settings on that tab and the Starters tab will also display a new list relevant to these settings.
Enhancement | An inline search form was added to the Turnover Leavers report.
Enhancement | The HR Generalist (GHRGenEmployeeAccess_ST), HR Actor Org Unit Generalist (GHRGenEmployeeOrgUnitAccess_ST) and GHRGenEmployeeOrgUnitAccessLevel_ST security templates were updated to give access to the UpdateTermination, UpdateRehire, and UpdateHire actions on the Employee business class.
Enhancement | Pay Code Calculation Types Rate Shift Differential and Percent Shift Differential have a new Boolean that allows users to mark them to exclude base rate. This will allow for only the Shift Differential amount to be paid to an employee. A new field called Rate will be displayed in the Shift section of the Pay Code to assist with Percent Shift Differential calculations as they use the Rate of Pay to calculate Shift Amount. Pay Rate will no longer be displayed on the Time Record as it is not included in the calculation of the Time Record Amount. This enhancement has no toggle. As flagging this Boolean could change pay history there are edits against changing existing Pay Codes. To use this feature a new Pay Code would need to be added.
Enhancement | Logic for created '*HOME' location code has now been added at the Employee, Work Assignment, and Time Record level to ensure proper tax and payment calculations for hybrid workers.
Enhancement | The Tax Balancing Report contains a list of variances for the Gross to Net amount, Federal and Medicare Taxable Wages, and Social Security and Medicare Tax Amount. It will also list a report for Federal, State, and Local Taxable Wages and Tax Amounts. PDF files are available with Quarter-to-Date and Year-to-Date summary reports. The report also has the option to run against a W2 file to compare the generated Federal, State, and Local Taxes.
Enhancement | A new post upgrade action has been added to run a Standard Rebuild to get new reports only.
Enhancement | An inline search form was added to the Reinstated report.
Enhancement | Add a "default to true" in ConfigureTurnoverByDates field rules during creation.
Enhancement | An inline search form was added to the Position Changes report.
Enhancement | The Compliance Reporting feature's trial period is set to end on October 2025 instead of October 2024. This code modifies that date.
Enhancement | Instruction text was added to the existing Work Assignment Default Rule Audit report to indicate replication is necessary to accurately display the icons in the report. This can be accessed by Administrator and Generalist.
Enhancement | Thumbnail images were added to the lists of documents in Transition Management module.
Enhancement | Menu navigation experience of multiple Learning and Development webapps accessed by Learning Administrator, Local Learning Administrator, Content Administrator, Instructor and External Learner Administrator has been consolidated into the 7 menus; Resources, Catalog, Checklists, Registration and Completion, Social Groups, Maintenance, Administration within a single webapp Learning and Development that users gain access through security and the access to the screens is controlled with security policies. To turn on the new experience, go to Administrator > Utilities > Feature Toggles and select ‘Enable’ on the ‘Learning and Development Consolidated Webapp’ feature. When this feature is enabled, security policies for the roles of Admin_ST, LearningAdministrator_ST, LearningAdministratorActorOrgUnit_ST, LearningContentAdmin_ST, LearningInstructor_ST and ExternalLearnerAdministrator_ST are activated for ContinuousDevelopment webapp that is referred to as Learning and Development. Alongside giving access to the webapp these security policies restrict the access to specific screens within the webapp. When a customized security roles is used to grant access to the existing web applications, you will need to create a policy for each of the customized roles that are expected to give access to a specific webapp otherwise users will be unable to access the web application. These policies can be managed in Security Administrator > Administration > UI Access Control > Navigation panel. Note: Configurations will need to be examined and in some cases applied to the new pages/lists/forms within the new menu structure.
Enhancement | When employee records are imported from EmployeeImport and they do not contain an action tag, the action tag will be defaulted to "ImportHire". The Update Action Tags For Turnover Data action has also been modified to correct the audit log for any employee records that were created by ImportHire or ImportTerminate.
Enhancement | Activity, Development Plan, Certification ,Checklist, Checklist Task, Checklist Component Group, Test can support 36 characters for ID fields Activity, Development Plan, Certification ,Checklist, Checklist Task can support 200 characters for Description/Short Description fields Development Plan, Certification can support 100 characters for DisplayName fields Evaluation, Test, Component Group can support 100 characters for Description fields
Enhancement | Upon clicking 'Sync Catalog' from both 'OpenSesame' and 'LinkedIn Learning' Direct Integrations provider field will be automatically populated and not editable
Issue | The logic that creates the employee time records was adjusted to ensure the accuracy of the time record generated. The system now generates a separate time record for an add-on rate or add-on percent of the pay rate with the correct hours and amounts based on the setup.