## Slide 1
Change Liaison Meeting
November 3rd, 2021

## Slide 2: Welcome!
Thank you for being here!
Expectations:
  Please give presenters your full attention.
  Please utilize the chat functionality (bottom right) to ask questions, or wait until the end of the presentation to come off of mute and ask.
  This meeting is being recorded and will be provided in the follow-up email.

## Slide 3
AGENDA
Phase 1 Update
Phase 1 Activities
Phase 2 Update
Phase 2 Activities
Engagement Opportunities
Luma Event Calendar
Phase 1 & 2 Know Do Share Reports (K.D.S.R.)

## Slide 4
Luma Phase 1 Update

## Slide 5: Phase 1 Timeline
2021 |  |  |  |  |  | 2022 |  |  |  |  |  |  |  |  |  |  | 
Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
2021
May
Jun
Oct-Dec
2019
2020
Sherpa Budget Management Go-Live
Phase 1: Finance & Procurement
Luma Phase 1 Kick-Off
Jan-Dec
Luma Phase 1 FSCM Reset
Finance Go-Live
Supply Chain Go-Live
Architect
Configure & Prototype
Validate
Deploy
Support
Plan
FRICE-W Design & Build
Scenario Testing (SIT) 3
Collect Business Requirements
Training Development
End User
Training
User Acceptance (UAT)
Sprints, SIT1 and SIT2
Infor Enhancement Testing
Cutover Activities
We are here

## Slide 6: Activity Impact-o-meter: October - December
October |  |  |  | November |  |  |  |  | December |  |  | 
4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27
Activity
Legend:
Phase 1
Phase 2
FRICE-W Functional Specs – Enhancements
Allocations Build
FRICE-W Development
Infor Enhancement Development (Trust Accounting 11/17)
SIT3 Prep
UAT Prep
Unit Testing for Enhancements
Identify Trainers
Learning & Development Set-up
Knowledge Transfer Execution
Mock Cutover
Sustainment Planning
Enterprise Design
FRICE-W Design & Build
Impact-o-meter: MEDIUM
*Measures the impact activities have on Agencies

## Slide 7: Budget Update
All revised budgets were submitted by the deadline of October 22nd.
  Statutorily driven exception budgets are due Nov 15th.
With our smaller team, over 20 major revision issues addressed in the final week before revision submission.
Further review and training will happen November 5th for DFM analysts to increase familiarity of the bifurcation process and using their specific commenting features.
The team is continuing engagement with the budget management functions of the Luma Finance modules.
Finalizing steps of last outstanding interfaces and digging into data requirements for the final two.
Sharing lessons learned from Luma Budget go live, training, and first cycle operation as appropriate with other Luma Teams.
The project team is currently working on creating a Feedback Survey for the Budget module.

## Slide 8: Approval Workflow
Timeline
Kick-off sessions:
9/27 & 9/29
Agency Workbook Completion:
Due 11/1
Size Distribution

## Slide 9: Luma (Security) Roles
Timeline
Workbooks sent:
10/13
Luma Roles Showcase:
10/21
Agency Workbook Due Date:
11/12
36
Luma Roles
All
Finance
Procurement

## Slide 10: Projects & Grants
Thank you to everyone who attended the Projects & Grants Workshop!
Next Office Hours session is on November 4th
@ 11 am
Q&A is posted on the Luma P&G webpage here
Workbooks due by November 15th.
Thank you to those that submitted Customer List workbooks by October 29th. Keep them coming!

## Slide 11: Interfaces
Chart: FRICE-W
| Forms | Reports | Interfaces | Conversions | Enhancements | Workflows
Completed | 1 | 4 | 102 | 38 | 1 | 18
Remaining | 0 | 24 | 87 | 9 | 0 | 1
Chart: FRICE-W Progress
| FRICE-W
Completed | 157
Completed Last Month | 7
Remaining | 121

## Slide 12
Luma Phase 1 Activities

## Slide 13: System Integration Testing (SIT) 3
Objective:
Confirms that business processes work as designed across all modules, FRICE-W components, and 3rd party integrated applications.
Testing with “final” security configuration in place
Scope:
All Functional Scenarios identified by Project team including End to End Scenarios
Re-execution of all FRICE-W Testing Scenarios
Simulation of a production business environment
  Fully converted data set – real/live data
Functional teams will identify which agencies to test by scenarios

## Slide 14: System Integration Testing (SIT) 3
Goals:
  Project team and agencies confident that Luma will enable the State of Idaho to support business operations.
  Project team confident that Luma is working as designed and configured.
  Agencies understand SIT purpose and agree to expectations.
Success Factors:
  No critical or high defects. (view exit criteria #3)
  Go-live required FRICE-W tested successfully.
  Roles and permissions tested and support the business operation requirements.
  Core State business processes required for Go-live be tested. (Detail List with exceptions identified)
  Timely and proper execution of the Testing Execution plan.
  Agencies complete assigned test scenarios.

## Slide 15: System Integration Testing (SIT) 3
Entry Criteria
Integration test scenarios are approved, set up in ALM (test management tool), and assigned to the testing team.
Exit criteria for SIT 2 is met.
All test data has been created and made available for execution.
Testing Environment is fully built, and data conversions have been executed and validated.
All required FRICE-W objects have been migrated and made available for execution.
Required access is provided to team members.
The defect management tool is set up and ready to use. (ServiceNow)
All defects from SIT 1 & 2 that still require resolution have been documented and communicated to key stakeholders.
Exit Criteria
All executable integration test cases have been executed.
Non-executable (non-testable) test cases have been listed and provided with reasons of non-execution. A further action plan is created.
No severity “High” or “Critical” defects are present, or an approved remediation plan is in place.
All known remaining severity defects still requiring resolution for testing have been documented and communicated to the key stakeholders.

## Slide 16: System Integration Testing (SIT) 3
SIT 3 |  | 
 | Start Date | End Date
Planning | 10/4/2021 | 11/5/2021
Setup | 11/8/2021 | 1/3/2022
Execution | 1/3/2022 | 2/18/2022
Remediation | 2/21/2022 | 3/11/2022
Timeline

## Slide 17: System Integration Testing (SIT) 3
0. Planning
Engage Agencies during Monthly Change Liaison Meeting (10/6)
Complete SIT 3 planning (11/5)
Request Agencies SIT 3 Files (11/5)
Complete Updates to Pristine (11/10)
1. Test Scenario Build Out
Identify Agency Participation (11/5)
Identify SIT 3 Scenarios (11/19)
Copy PRISTINE to DEM (11/19)
Updates to Agency Workbooks (11/19)
Agencies provide SIT 3 Data Files (11/19)
2. Finalizing Testing
Meet with Agencies to identify Testers (12/3)
Update Scripts/scenarios in ALM (12/3)
Finalize Security Roles for SIT 3 (12/3)
Agencies Identify Tester (12/10)
Complete FRICE-W Testing (12/15)
Finalize Testing Schedule (12/17)
Complete Testing Data Sheets (12/17)
4. SIT 3 Kick off and Execution
Complete SIT 3 Security Roles Setup (1/5)
SIT 3 Agency Kick off (1/3-1/7)
SIT 3 Execution (1/3)
We are here!
Complete DEM Build/Configuration (12/17)
Send Agency Meeting Invites (12/17)
3. Finalize Build and Send out Invites

## Slide 18: System Integration Testing (SIT) 3
Nov 3
SIT 3 Overview
Provide SIT 3 Introduction at monthly Change Liaison meeting.
Dec 10
Identify Agency Tester
  Agencies to provide list of Agency Testers to Luma Project Team
Jan 3-7
SIT 3 Kick Off
Dec 17
Calendar Invites
  Agencies will receive for SIT 3 calendar invites
Nov 5
Notify Participants
  Provide list of agencies selected for participation, including explanation based on criteria.
Jan 3 - Feb 18
SIT 3 Execution
  SIT 3 agency involvement will begin the week of 1/3 for FRICE-W and 1/14 for functional scenarios

## Slide 19: System Integration Testing (SIT) 3
Utilize 11 Core End-to-End Business Scenarios identified by Luma Team Members during SIT planning
Another pass with functional teams to gather test scenarios for SIT 3 (align to lvl 3 BPR’s to complete end-to-end testing)
All FRICE-W objects will be tested in SIT 3 once more

## Slide 20: System Integration Testing (SIT) 3
FRICE-W Testing
First 2 weeks: (Jan 3 – Jan 14)
FRICE-W: Conversion/Inbound interfaces
Middle 4 weeks: (Jan 17 – Feb 11)
FRICE-W: Workflows/approvals
Last 2 weeks: (Feb 7 – Feb 18)
FRICE-W: Outbound/Reports
Functional/Other Testing
Middle 4 weeks: (Jan 17 – Feb 11)
End to End Scenarios (10-20 agencies max)
Any additional functional scenarios identified by workstreams
Last 2 weeks: (Feb 7 – Feb 18)
Additional Security Testing
  Security will be tested throughout the entirety of SIT 3 not just the last two weeks. The last two weeks will focus on any additional agency specific or negative security testing.

## Slide 21: System Integration Testing (SIT) 3
  The Test Management Team will host an all-day SIT Testing Support Line (WebEx Meeting)
    Attendance is optional and SIT testers should only join if they have questions or issues regarding SIT Testing.
    The Meeting Moderator will reach out to Test Management, Functional, or Technical Teams if they need additional help resolving an issue
  Schedule:
    Monday – Thursday
      8:45 AM MT - 11AM MT
      1:45 PM MT – 4:00 PM MT
    Friday
      9AM MT – 11 AM MT
Roles | Responsibilities | Staffing
Test Management Team (Meeting Moderators) | Field SIT Testing Questions/Issues and triage to support teams as necessary Be ready to answer any questions regarding ALM or Reporting | Minimum of 1 person always while meeting is in session
Functional Team Members | Be available to answer any questions regarding Infor, Scripts, or Data | On Call
Technical Team Members | Be available to answer any questions regarding Security/Access or FRICE-W defects | On Call

## Slide 22
Luma Phase 2 Update

## Slide 23
Early Phase 1, technical information
gathering, surveys, and analysis
JUL
AUG
SEP
NOV
JAN
DEC
50+ BPR sessions
Infor Orientations
Phase 2 Luma Base Configure

OCT
FEB
MAY
JUN
JUL
AUG
SEP
OCT
NOV
DEC
Finished six BPR weeks
+ 105 Process Maps
> 161 Change Impacts
+ 100 State SME’s
~ 50 BPR sessions
Nearly 10,000 people hours
Configuration
Workshops
Jan 13, 2022
infor 7.2 WFM Multi- Tenant Commercial
Sprint 3
Sprint 1
Sprint 2
User Validation of Luma Functions
Conversion Building
Interface Building
Practice Conversion
Interface Testing
Payroll/Time
Compare 1
2
3
Scenario Testing
User Story Integration
End to End
Agency Life Cycles
Employee Life Cycles
Using requirements, process maps, user stories and functional roles, Deloitte will build the three Phase 2 components of Luma (HR, Payroll, and Time (WFM)) with input from
Amber’s Core Team (Payroll and Time (WFM)) and
Ashleigh’s Core Team (HR)
P2 Scope
Defined
Get End User Needs/Change Impacts
End User Training Developed
End
User
Training
Go Live
Monitor
No Showstoppers
Create Workarounds
infor 7.2 WFM
Multi-Tenant Government
Training Tested
User Acceptance Testing
SCOPE MANAGEMENT
QUALITY ASSURANCE
IMPLEMENTATION READINESS
OPERATE 
Configuration Architects
“Knowledge
Transfer”
Schedule

APR
MAR

## Slide 24
Luma Phase 2 Activities

## Slide 25: Payroll/HR Survey
The Luma Project team is working on a survey to gather more information for Payroll & HR.
As of today, this survey can be expected no later than November 15th.

## Slide 26
Engagement Opportunities

## Slide 27: Engagement Opportunities
Type of Engagement | Date | Time | Topic
November Procurement Learning Lab Option # 1 | November 16th | 10:00 am | Sourcing Events & Supplier Portal
November Procurement Learning Lab Option # 2 | November 18th | 2:00 pm | Sourcing Events & Supplier Portal
Statewide Showcase | November | 1:00 pm | None
Upcoming engagement opportunities to learn more about Luma. Please help us spread the word!

## Slide 28
Event Calendar
State of Idaho Controller's Office Website

## Slide 29
Know Do Share Report
(K.D.S.R.)

## Slide 30
Please share this information or engagement opportunities with your Agency
Phase 1 K.D.S.R.
KNOW
DO
SHARE
REPORT
Read Luma Project news and updates in this column.
Meet with employees and leadership in your agency to discuss these messages or action items.
Luma Learning Labs:
What: Sourcing Events & Supplier Portal
When: November 16th | 10 - 11am
November 18th | 2 - 3 pm
Where: Virtual meeting. Use the link below to RSVP!
Webpage Links:
Change Liaison Dashboard (idaho.gov)
EventsCalendar (idaho.gov)
Report feedback to the project team or complete action items the Luma project team is requesting from your agency.
Internal Meetings: Please let us know if you have an upcoming internal meetings that we can present to your staff! We want every state employee to know about the Luma, the changes coming, and exciting benefits of a modern system.
November 3rd, 2021
If your agency is currently working with the Luma Project team on an interface or conversion, please maintain momentum to bring those to completion.
Approval Workflow: Keep submitting workbooks if you have not already.
Security Roles: This workbook is due back to your Agency Advocate by November 12th.
Projects & Grants: The Luma P&G team will be holding another office hours session tomorrow at 11 am. The workbooks are due by November 15th.
Custodial Accounts/Allocation Workbooks: The Luma Project team is currently meeting with a select group of agencies to update and validate these workbooks.
Phase 1 Go-live: Phase 1 of the Luma Project will go live on July 1st, 2022 with the Finance and Procurement modules.
SIT 3 Prep: The project team will be notifying SIT 3 participants on 11/5.
Change Readiness Assessment - Measurement 3: Thank you to everyone who completed our third CRA measurement!
RSVP Here

## Slide 31
Please share this information or engagement opportunities with your Agency
Phase 2 K.D.S.R.
KNOW
DO
SHARE
REPORT
Read Luma Project news and updates in this column.
Meet with employees and leadership in your agency to discuss these messages or action items.
Report feedback to the project team or complete action items the Luma project team is requesting from your agency.
Internal Meetings: Please let us know if you have an upcoming internal meetings that we can present to your staff! We want every state employee to know about the Luma, the changes coming, and exciting benefits of a modern system.
Phase 2 Go-live: Phase 2 of the Luma project will go live with Workforce Management/Time in December of 2022 and Payroll as well as Human Capital Management on January 1st, 2023.
BPR Update: Thank you to everyone who participated in the Phase 2 BPR sessions!
Payroll/HR Surveys: The Phase 2 project team is working on a survey to gather more information from agencies. This can be expected no later than November 15th. More information to come!
Phase 2 Luma Webpages:
EventsCalendar (idaho.gov)
BPR Webpage: Luma Phase 2 Business Process Redesign (idaho.gov)
Payroll: Luma Payroll Module (idaho.gov)
Human Capital Management: Luma Human Capital Management (idaho.gov)
November 3rd, 2021
Nothing this month!

## Slide 32
Questions

## Slide 33
Thank You!
Sheena Coles
SColes@sco.Idaho.gov
208-334-3100
Alex Doench
adoench@sco.Idaho.gov
208-332-8841
Danielle Blackmer dblackmer@sco.Idaho.gov
208-332-8868
Chris Lehosit clehosit@sco.Idaho.gov 208-332-8887
Tina Fuller tfuller@sco.Idaho.gov 208-332-8867
Elijah Stearns
estearns@sco.idaho.gov 208-332-8871