## Slide 1
Change Liaison Meeting
October 5th, 2022

## Slide 2: Welcome!
Thank you for being here!
Expectations:
  Please give presenters your full attention.
  Please utilize the chat functionality (bottom right) to ask questions, or wait until the end of the presentation to come off of mute and ask.
  This meeting is being recorded and will be provided in the follow-up email.

## Slide 3
AGENDA
Phase 1 Update
Phase 2 Update
Key Takeaways

## Slide 4
Luma Phase 1 Update

## Slide 5
Phase 1 Earliest Possible Go-Live
Go Live
January 1st will not be the earliest possible go-live for Phase 1.
The Project management team and governance board are currently assessing the viability of a “big bang” (phase 1 and phase 2) go-live in June/July.

## Slide 6
Phase 1 Roadmap through October (June 7, 2022)
MAY
JUN
JUL
AUG
SEP
OCT
APR
We are here
Phase1: Pre-SIT Initiatives
Pristine Build
Mock CO
Dress Rehearsal
End User Training
Final Cutover
Go Live
Tenant Management Plan
Test Strategy
Cutover Plan
Internal SIT
Initiatives Build
Configuration
Agency Partnership Activities
DASHBOARD
Readiness for System Integration Testing (SIT)
mid-May to mid-August
  Business Process Validation (unfinished and SIT critical)
  Tenant setup and management
  COA structure gathered and loaded
  FRICE-W required
Scope / readiness
  Agency Open Business Process Reviews
  Gap and Enhancement Management
  Projects and Grants Workbooks
Configuration Implementation Schedule
  Agency Configuration Workbooks
  Projects and Grants Workbooks
  Agency Functional Workshops
Agency SIT
Update | Phase 1 Schedule Planned

## Slide 7
Testing of All Interfaces
Phase 1 October Schedule of Events
Remediation Done
Oct 3-7
Oct 10-14
Oct 24-28
Objective: Test All Interfaces, Conversions, and Business Processes
Testing Complete
System Ready
Agency Business Process Testing
Oct 17-21
System Preparation (Data and Configuration)
Defect Remediation
Luma Phase 1 Overarching Project Plan
Week 5 – Agency Participants
Week 6 – Agency Participants
Week 7 – Agency Participants
Week 8 – Remediation
Critical Enhancements***CU Testing
Go-Live Viable

## Slide 8
Successfully completed three-week internal SIT
  Engaged and Passed 82% of test scripts (1,367 out of 1,687)
  P&G workbook response – 53 of 53 agencies – 100%
  GL required workbooks – 83 agencies – 100%
  Conversion records processed 98% success – 333k out of 340K
  Remaining test scripts dedicated to interface testing over next 4 weeks
  Resolved 75 out of 116 incidents – remediation next 4 weeks (58% security)
Scope lock valid – no new mission-critical functionality gaps
On track for Agency-Focused SIT – Started Monday, September 26th
  P&G Agency SIT – In-Person Workshop and Testing- 9/26 – 9/30
  Expanded Agency SIT – In Person - 10/3 – 10/21
Revalidated Cash double entry enhancement (December)
Workbook delivery by agencies needs greater communication
P&G workbooks and balances are extremely time-consuming
Greater system performance testing required
Work Force transition and readiness – time for training materials
Remaining enhancements need design, build, and test
Interface testing and validation requires greater collaboration
P&G balance collection action by agencies requires extra attention
Accomplishments
Challenges
Risks
Phase 1 SIT Updates

## Slide 9: Workforce transition
Leadership Accelerator
Targets senior management and influential stakeholders. Content focuses on statewide benefits, recommendations for how to become an effective catalyst for change.
Persona Workshops
Content-specific for employees based on their Persona. Details future state through “Day in the Life” storytelling, including future benefits, highlighting new tasks and important changes.
User Experience Simulations
Interactive simulations of common tasks (e.g. submitting a timecard, accessing paystubs, viewing assigned workflow items).
Prepare agency employees to understand the changes to roles, responsibilities, and tasks to successfully adopt Luma and realize the intended benefits.
COMPONENTS
KEY DATES
Leadership Accelerator Workshops Start
Luma Phase 2 Personas Workshops Start
User Experience Simulations Available
End of Oct/Nov
November 2022
– Jan 2023
Feb- March 2023

## Slide 10
Luma Phase 2 Update

## Slide 11
We are here
Phase 2 (HCM)
October 4, 2022
Schedule
#2 Complete
SIT 2 & Pay Compare 1
JUL
AUG
SEP
OCT
NOV
Phase 1 Delivery:
>9 P&G/COA
finance structure
Pay/Time
Compare 1
System Integration
Testing 2
MC 1
Mock
CutOver
DEC
JAN
FEB
MAR
APR
1
8
15
11
18
25
22
29
5
12
19
26
3
10
17
24
31
7
14
21
28
5
12
19
26
2
9
16
23
30
6
13
20
27
6
13
20
27
3
System Integration
Test 1
6
13
20


MAY
JUN
Milestone #1
Start Testing


Additional Testing 2+
Scope Balancing
Pay/Time 1+
Go-Live
Readiness

## Slide 12
Phase 2 (HCM)
October 4, 2022
Performance Metrics

## Slide 13
Key Takeaways

## Slide 14
Thank You!
Danielle Stevens dstevens@sco.Idaho.gov
208-332-8868
Chris Lehosit clehosit@sco.Idaho.gov 208-332-8887
Sheena Coles
SColes@sco.Idaho.gov
208-334-3100
Alex Doench
adoench@sco.Idaho.gov
208-332-8841
Krystal Griffith
kgriffith@sco.Idaho.gov
208-332-8861